## Portal MVP
Issue key | Issue Type | Custom field (Linked Feature) | Summary | Description
ISERVE-548 | Feature (Agile) | ISERVE-323 | UI/UX Concepts (Vendor Deliverables WO2) | The iSERVE online experience *standards* will be determined and documented with this feature. These standards will be adhered to for any portal page. This includes but is not limited to: * ADA Compliance (see ISERVE-546) * Portal layout * Navigation * Color schemes * Font details * Logo * Help * Look and feel * Adaptability for screen size The deliverable includes documentation, wireframes, HTML.
ISERVE-545 | Feature (Agile) | ISERVE-323 | Register to Vote
ISERVE-350 | Feature (Agile) | ISERVE-323 | Online Help and Training | The Solution will provide online Solution documentation that is accessible at all times including, but not limited to: - Online policy and procedures - User guides - Solution help {color:#ff0000}GK - If we want people to be able to find their their own solutions through the documentation, the documents must be CLEAR and EASILY ACCESSIBLE. This will be a new system for some, so acceptance criteria really needs to emphasize this. What that means is subjective to each of us, but we want special care to ensure the interface is intuitive and the help instructions legible.
ISERVE-54 | Feature (Agile) | ISERVE-323 | Direct users to new Multi-Benefit "Application" Entry experience | The iServe Nebraska portal interface will display online activities and information to more quickly serve applicants and clients. This covers +what content+ is displayed on iServe. +Allows user to FIND:+ * iServe account creation/login (functionality found on Feature ISERVE-11) * Online application (functionality found on Feature ISERVE-41 and ISERVE-200) ** Medicaid ** Economic Assistance ** Developmental Disabilities * Anonymous Benefit Discovery tool (functionality addressed with Feature ISERVE-40) * File Uploads (functionality addressed with Feature ISERVE-43 and ISERVE-579) * Secure Messaging (functionality addressed with Feature ISERVE-42) * Alerts (functionality addressed with Feature ISERVE-?) * Online Help (functionality addressed with Feature ISERVE-350) +Addresses Pain Points identified with Access Nebraska+ * What can I do online?
ISERVE-40 | Feature (Agile) | ISERVE-323 | Benefit Discovery | Benefit Discovery answers the "Do I qualify" question for a guest visiting DHHS online. * The tool is an easy way to find out if a person might be eligible to receive benefits by answering a few short questions on the household's current conditions. * This is a basic screening tool and not an application for benefits. * The tool captures key information, such as - age, citizenship, pre-conditions (e.g. pregnant, disability, veteran, income, household number, current enrollment, full/parttime. * The tool provides feedback on benefit eligibility. Even if the pre-screening tool indicates that the applicant may not be eligible, the applicant may still complete an official IE application to get an official decision about their (or household) eligibility. * {color:#ff0000}Prescreening tool acts as an education point for applicants, informing them of potential programs available within DHHS and gearing the applicant towards these programs, rather than experiencing misses through interactions.
ISERVE-44 | Feature (Agile) | ISERVE-323 | Improving User Experience using latest UX/UI standards | (Actual UX/UI paper deliverable detailing iSERVE standards will be tracked using Feature ISERVE-548) +Improve user experience using updated UX/UI+ * Create a visually appealing online presence/experience/brand using Marketing approved images, colors, icons, and fonts * Allow for intuitive navigation and site usage. This can be achieved with layout designs that clearly steer the visitor to common activities and information as well as using industry standards for mouse/keyboard navigation * Display information so it is easily viewed and understood * Ensure that various devices can be used to access this information by providing responsive screen sizing * Ensure that various browsers can be used to access site as expected +Addresses the following Pain Points identified with Access Nebraska+ * Too much stuff * Where do I go? * Similar icons/colors/labels for different paths/actions * Inconsistent labels/text for the same path/actions * Misspelling * Want mobile app
ISERVE-42 | Feature (Agile) | ISERVE-323 | Communicate with Clients | Asynchronous (e.g. email) messaging between system users (e.g. Clients, DHHS staff).
ISERVE-654 | Feature (Agile) | ISERVE-520 | Identity Cross-Reference Service | A cross-reference service is required to associate authenticated user accounts with unique identifiers required to retrieve user data (e.g. Medicaid data) from other DHHS systems. This service will be utilized by the APIs created by the interoperability project.
ISERVE-644 | Feature (Agile) | ISERVE-520 | Authentication Service | An authentication service is required to manage accounts for the iServe portal. Additionally, this service will be leveraged by the interoperability project to authenticate users attempting to pull Medicaid data through 3rd party applications.
ISERVE-625 | Feature (Agile) | ISERVE-520 | Role Base Permissions/Security Maintenance | Each iServe Account should have specific security assigned to it to ensure information is secured on the portal and only available to those accounts authorized to view, modify, or add that information.
ISERVE-11 | Feature (Agile) | ISERVE-520 | Create and Maintain Account Login/Logout | Provide the ability for a User to create an iServe Nebraska Portal account and log-in/log-out of their iServe Nebraska Portal Account. Only Users with newly created or existing iServe Nebraska accounts can log-in/log-out of the iServe Nebraska Portal . ¦User has access to a computing device (e.g., desktop/laptop) or mobile device (e.g., iPhone, Android) with an internet browser (e.g., Google Chrome, Mozilla Firefox, Apple Safari)¦ iServe Nebraska Portal users for Portal MVP, include the following stakeholder groups: * Applicant * Client * Parent or Legal Guardian of Client
ISERVE-579 | Feature (Agile) | ISERVE-322 | Client Copy of Application Details | A client copy of entered application information is requested as part of their application experience.
ISERVE-523 | Feature (Agile) | ISERVE-322 | Capture/track Client Consents and Authorizations | This is a subset of the online application experience specific to the client consents and authorizations DHHS is required to collect from applicants.
ISERVE-200 | Feature (Agile) | ISERVE-322 | Automatically provide application data from initial app entry for Eligibility Determination to N-FOCUS | Application Data will automated to feed into existing N-Focus interfaces replacing many manual efforts like keying the pdf. The following information should update to N-Focus automatically: * HH members * Tax HH * Tax Permission * Address * Phone * Email * Client preference
ISERVE-41 | Feature (Agile) | ISERVE-322 | Complete and Submit Multi-Benefit Application | Online single application accessible from local computer or mobile device that allows an applicant to be considered for Medicaid, Economic Assistance, and HCBS(Development Disabilities) Benefits through Nebraska DHHS.
ISERVE-43 | Feature (Agile) | ISERVE-322 | Submit Additional Documentation (aka File Upload) | Allow a Portal Account User to upload files to their Portal Account or an IE Application. Files can be uploaded: * directly to user account document repository * during application submission * within a message ** {color:#FF0000}Would like the ability for the client to self determine the category of said documentation. ZC
ISERVE-677 | Story | ISERVE-200 | Magi Route Marital Status - Manual Decision | Marital Status is a required field in N-Focus and manually set by Case Worker for MAGI route off of known information from application because online Magi application does not collect this information. It is on paper application. CMS did not approve collection on online. Open discussion item with CMS SPA Track for iServe.
ISERVE-566 | Story | ISERVE-200 | N-FOCUS Check for duplicate before creating master case | Need to build in integration processing to replace manually driven process that prevents duplicates. Example: If application comes in and Greg picks it up from pend/tie process, he searches for a duplicate master case. If there is a duplicate, he then ..... GK - Short answer is I use that master case as the case that the program case will be opened in. There are variables though in determining if the program case itself is a duplicate or if it needs a new program case in the same or new Master Case. * SNAP is requested by a family member who has turned 22. * Medicaid is requested by a family member who has turned 19. * Household members do not share food with the Head of HH (Energy Only - EO) * Pregnancy of a minor HH member. * HH member has moved. * State Ward situation. Most cases are simple enough to determine, but in the event of SSN, name, address and phone are not included on the application, or are incorrect, further research can be required to determine if a user is currently in the system and/or a member of a master case. {color:#de350b}Ã˜Workers will search NFOCUS to find a master case using information such as master case number, first and last name, address, phone number or Social Security number GK - The order is to try SSN (of all listed on application if applicant is not found), name (including previous name if listed), address then phone. Ã˜Create new master cases when an existing master case is not found (last resort) GK - New master case is created if one is not found, but also if it is determined that the individual is not in the HH anymore or any other reason that makes it appropriate for a new MC. If an application is received for those that are already eligible, the application is determined a duplicate, in which case it is viewed as a changed report and reviewed for any updates. This story, as it pertains to auto-filling information into our system (at present NFOCUS) may need to have a degree of manual intervention. {color:#de350b}GK - A way of segregating applications that need further review may be needed. {color:#de350b}In the even that the application shows a change in HH, this may cause the application to be in fact considered an initial application (although in MEDICAID, a new application is not needed in event of a HH change, but in HCBS and EA, this may not be the case)
ISERVE-586 | Story | ISERVE-40 | Benefit Discovery: Save User Results to iServe account | As an iServe site visitor, who completed Benefit Discovery, I want to be able to save my Benefit Discovery results to my iServe account so that I have them for later reference. *Scope* * Able to save discovery results to iServe account * Display message when user chooses not to save results and then tries to navigate away from or close benefit discovery results ** Message should warn user that all information will be deleted if not saved * Externally saved results cannot be used to populate an application electronically *Design* * Determine how results will be used so team can determine best solution for saving ** reference the list only > save as text file or similar ** need potential to read some answers and pre-populate future applications > save as fields on user account " * Consider how results will be saved and maintained ** saved format (see design1) ** save more than one set of results? ** how to recall one set of results and use for new application?" * Check if user has an existing iServe Nebraska account ** If yes €“ request user to log-in ** If no - request user to create an account (from this screen?) *** will user be redirected away from benefit discovery results to create account? **** Will this affect saving results? ** Display message when results are successfully saved * Can multiple drafts be saved? (Why? What's the benefit?) ** {color:#de350b}ZC-Working on clarification as to if clients can save multiple pre-screens or if applicants must complete a started pre-screen before beginning a new
ISERVE-526 | Story | ISERVE-40 | Benefit Discovery: Display Results with supplemental resources | As an iServe site visitor, I want information on supplemental (community) resources when I get my benefit discovery results so that I know where to turn outside of DHHS for assistance. *Design notes* * Determine format for this information ** Link to an existing AccessNE site? ** New site with same info? ** Link to external site(s)?
ISERVE-358 | Story | ISERVE-40 | Benefit Discovery - DHHS Form Configuration for Economic Assistance | As a DHHS iServe Nebraska Admin, I want to have the ability to configure the Benefit Discovery input forms configuration for Economic Assistance; to include * ADC/EF/TANF * CC * SNAP * LIHEAP * Refugee Resettlement Program * SDP * SSAD/AABD? The configuration should include but not be limited to: * Age Range * Disabled or Blind (Y/N) * Developmental Disability (Y/N) * Current Pregnancy Status (Y/N) * Nursing Home (Y/N) * Assisted Living Facility (Y/N) * Resource Range * HH Size * Income Range * Student Status (Y/N) * Citizenship (Y/N)
ISERVE-361 | Story | ISERVE-40 | Benefit Discovery - DHHS form configuration for Commonality Points | As a DHHS iServe Nebraska Admin, I want to have the ability to configure the Benefit Discovery input forms configuration for commonality points. Commonality Points would be situations in which questions span across multiple agencies and programs. The configuration should include but not be limited to: * Age Range * Sex (M/F) * Health Insurance Coverage (Y/N) * Disabled or Blind (Y/N) * Developmental Disability (Y/N) * Current Pregnancy Status (Y/N) * Nursing Home (Y/N) * Assisted Living Facility (Y/N)
ISERVE-359 | Story | ISERVE-40 | Benefit Discovery - DHHS form configuration for Medicaid | As a DHHS iServe Nebraska Admin, I want to have the ability to configure the Benefit Discovery input forms configuration for Medicaid to include * Medicaid * CHIP * 599 CHIP * SRT * EMSA * PAS * HHA The configuration should include but not be limited to: * Age Range * Sex (M/F) * Health Insurance Coverage (Y/N) * Disabled or Blind (Y/N) * Developmental Disability (Y/N) * Current Pregnancy Status (Y/N) * Nursing Home (Y/N) * Assisted Living Facility (Y/N) * Income Range * Resource Range * Household size * Citizenship Status (Y/N) * Emergency Need (Y/N) * HHA may expand as it is developed to include client participation criteria
ISERVE-360 | Story | ISERVE-40 | Benefit Discovery - DHHS Form Configuration for Developmental Disabilities (HCBS) | As a DHHS iServe Nebraska Admin, I want to have the ability to configure the Benefit Discovery input forms configuration for HCBS (home and community based services). * PACE * TBI * AD * DD * EDN The configuration should include but not be limited to: * Age Range * Sex (M/F) * Medicaid Approval Status (Eligible/Ineligible)(SRT) * Disabled or Blind (Y/N) * Developmental Disability (Y/N) * Nursing Home (Y/N) * Assisted Living Facility (Y/N) * Zip Code * Previous Medical History * Traumatic Brain Injury (Y/N)
ISERVE-72 | Story | ISERVE-40 | Benefit Discovery: Redirect to Start Application | As an iServe site visitor, who completed Benefit Discovery, I want the option to move directly into a new application so that the relevant discovery answers can be included automatically in the application and potentially save time. *Scope* * User can choose to start application from the Benefit Discovery Results screen * Results from relevant discovery answers are used to pre-populate related fields in the newly started application ** (See Design grid to identify relevant answers and related appl fields as well as the variations based on how discovery question was answered)" ** {color:#00875a}Should pre-populating data be tested here or in one of the "Start Application" scenarios? *Design notes* * Open new application from Benefit discovery results and pass relevant data for pre-population * Identify relevant discovery answers * Determine how relevant answers should pre-populate in related appl fields * Consider what happens to temporarily stored benefit discovery data once application is started ** Without official "Save" functionality (address in ISERVE-70), can benefit discovery inputs be temporarily saved and passed into iServe app if user closes out of benefit discovery and re-opens tool? ** What amount of time can Benefit Discovery results be displayed before screen times out? *** scenario: visitor completes benefit discovery and wants to start appl but goes to gather information. App isn't started and account doesn't exist to hold saved data.
ISERVE-70 | Story | ISERVE-40 | Benefit Discovery: Save User Results externally | As an iServe site visitor, who completed Benefit Discovery, I want to be able to save my Benefit Discovery results so that I have them for later reference. *Scope* * Able to save discovery results to a valid destination external to the iServe site * Display message when user chooses not to save results and then tries to navigate away from or close benefit discovery results ** Message should warn user that all information will be deleted if not saved * Externally saved results cannot be used to populate an application electronically *Design* * Determine document format(s) * Consider various destinations ** Hard drive of PC/MAC ** Shared/Network drive of PC/MAC ** Storage for Mobile device ** Web-based shared drive for Mobile device (i.e. google drives, dropbox, etc...) ** Application for Mobile device (i.e. google drives, PDF reader, etc...) ** To PDF (saved to device or application folder)"
ISERVE-58 | Story | ISERVE-40 | Benefit Discovery: Utilize online tool to see potential benefit programs | As an iServe site visitor, I want to complete an anonymous benefit discovery so that I can determine potential benefit programs for which I may be eligible. *Scope* * User is presented with a short series of questions * Results clearly display which program(s) user may qualify for (See Design grid for "Results") * Information is readable at Flesch-Kincaid 4th grade level (Accessibility) * Information is presented in user preferred language (Accessibility) * User can review inputs and make changes * User can retake questionnaire multiple times without restriction +The next set of ACs may be a part of this story or potentially break off into other story(s):+ * {color:#00875a}Help features are available to help user understand/complete benefit discovery ** {color:#00875a}Link to FAQs ** {color:#00875a}Links to Program descriptions ** {color:#00875a}Field information, where needed * {color:#00875a}Information is searchable (Accessibility) ** {color:#00875a}"What does this mean for Discovery? How would a user search?" * {color:#00875a}DHHS Admin Role can change labels, location, configure the content for €¦ {color:#00875a} Emergency Assistance/ ADC / TANF / AABD / LIHEAP ** {color:#00875a}What does this mean for Benefit Discovery? Do we want DHHS IT to be able to do *** {color:#00875a}Add/Remove/Edit/Move Questions *** {color:#00875a}Add/Remove/Edit Results" The following Stories were cancelled as they now appear as Acceptance Criteria for this story: ISERVE-68 ISERVE-525 ISERVE-69 ISERVE-19 ISERVE-524 ISERVE-71 *Design notes* * User is presented with a short series of conditional questions ** {color:#00875a}<attach question flow when finalized> * DHHS staff specify field types for each Benefit Discovery form field * DHHS staff define business rules for each Benefit Discovery form field * DHHS verifies accuracy of Results grid ** Grid shows each set of results that could be displayed based on questionnaire responses ** {color:#00875a}<attach results grid when finalized>
ISERVE-29 | Story | ISERVE-40 | Benefit Discovery: User Print | As an iSERVE site visitor, who completed Benefit Discovery, I want to be able to print my Benefit Discovery results so that I have them for later reference. *Design* * Determine print format * Consider various printer destinations ** LAN/Wifi printer from PC/MAC ** WiFi printer from mobile device ** To PDF (saved to device or should this be a ""save"" option rather than print?)" Output options: * Information that was entered in the prescreening fields * May also include: ** office location*{color:#57d9a3}/phone number * information ** information on applying ** today's date ** *{color:#57d9a3}list of possible programs client may be eligible for * ** *{color:#57d9a3}website address * ** *{color:#57d9a3}Example below on how the current results looks like when printed * {color:#de350b}*ZC- is this a question for the vendor when they come one? Not sure if this is all necessary information*
ISERVE-636 | Story | ISERVE-42 | SNAP - Application Withdraw | As a SNAP Applicant, I want to withdraw my SNAP application that I submitted via iServe Nebraska Portal so that it does not process through eligibility determination.
ISERVE-562 | Story | ISERVE-42 | Non-Discrimination Statement | As an applicant, I want to see DHHS's non-discrimination statement as part of my application experience. {color:#00875a}CIVIL RIGHTS {color:#00875a} This institution is prohibited from discriminating on the basis of race, color, national origin, disability, age, sex and in {color:#00875a} some cases religion or political beliefs. {color:#00875a} The U.S. Department of Agriculture also prohibits discrimination based on race, color, national origin, sex, religious {color:#00875a} creed, disability, age, political beliefs, or reprisal or retaliation for prior civil rights activity, in any program or activity {color:#00875a} conducted or funded by USDA. {color:#00875a} Persons with disabilities who require alternative means of communication for program information (e.g., Braille, {color:#00875a} large print, audiotape, American Sign Language, etc.), should contact the Agency (State or local) where they {color:#00875a} applied for benefits. Individuals who are deaf, hard of hearing or have speech disabilities may contact USDA {color:#00875a} through the Federal Relay Service at (800) 877-8339. Additionally, program information may be made available in {color:#00875a} languages other than English. {color:#00875a} To file a complaint of discrimination, complete the USDA Program Discrimination Complaint Form, (AD-3027), {color:#00875a} found online at: [http://www.ascr.usda.gov/complaint_filing_cust.html], and at any USDA office, or write a letter {color:#00875a} addressed to USDA and provide in the letter all of the information requested in the form. To request a copy of the {color:#00875a} complaint form, call (866) 632-9992. Submit your completed form or letter to USDA by: {color:#00875a} 1. mail: U.S. Department of Agriculture, Office of the Assistant Secretary for Civil Rights, 1400 Independence {color:#00875a} Avenue, SW, Washington, D.C. 20250-9410 {color:#00875a} 2. fax: (202) 690-7442; or email: program.intake@usda.gov. {color:#00875a} For any other information dealing with Supplemental Nutrition Assistance Program (SNAP) issues, persons should {color:#00875a} either contact the USDA SNAP Hotline Number at (800) 221-5689, which is also in Spanish or call the State {color:#00875a} Information/Hotline Numbers (click the link for a listing of hotline numbers by State); found online at: {color:#00875a} [http://www.fns.usda.gov/snap/contact_info/hotlines.htm]. {color:#00875a} To file a complaint of discrimination regarding a program receiving Federal financial assistance through {color:#00875a} the U.S. Department of Health and Human Services (HHS), write: HHS Director, Office for Civil Rights, {color:#00875a} Room 515-F, 200 Independence Avenue, S.W., Washington, D.C. 20201 or call (202) 619-0403 (voice) or {color:#00875a} (800) 537-7697 (TTY). {color:#00875a} This institution is an equal opportunity provider.
ISERVE-535 | Story | ISERVE-42 | Messaging: 2. View Secure Messages | As a Client, I want to view the emails in my inbox so I can be knowledgeable about my programs and services. ToDo: * Identify how many messages can be displayed settings? Is this configurable? *{color:#00875a}Mickey - most sites have 10 messages displayed at a time and offer a drop down to view up to 50 at a time * *{color:#00875a}Once message is read client has the option to delete or leave message in inbox for future reference * *{color:#00875a}User should be able to sort messages by unread *
ISERVE-187 | Story | ISERVE-42 | Messaging: 3cii. Upload File | As a DHHS Client, I want to be able upload a file to associate with a message so I can provide necessary documentation to DHHS. Process Flow: !image-2021-01-05-19-34-32-369.png! This process follows same rules as Story # +*ToDo:*+ * Screen Mockup +*Open Questions:*+ * Is there a limit to number of files that can be uploaded? * WHere can files be uploaded from....See story #...
ISERVE-188 | Story | ISERVE-42 | Messaging: 3di. Alert sent via communication preferences | As a DHHS Client, Upon sending a message I want to receive an alert via my account profile communication preference settings (email/text). {color:#0747a6}KJA - Do we want to give users the option to turn this off? ToDo: * Mockup Needed
ISERVE-180 | Story | ISERVE-42 | Messaging: 1. Secure Inbox Access | As a Client, I want to access my secure inbox so I can review my messages. ToDo: * Identify where this is visually on the Portal Homepage / dashboard {color:#ff0000}GK - I think this could be on the lower part of the screen. Or can a person eventually configure their own dashboard? A simple envelope icon with numbers of unread messages for a default. * Mockup Screen * Identify how many messages can be displayed settings? Is this configurable? *{color:#00875a}Mickey - most sites have 10 messages displayed at a time and offer a drop down to view up to 50 at a time * *{color:#00875a}Once message is read client has the option to delete or leave message in inbox for future reference * *{color:#00875a}User should be able to sort messages by unread * *{color:#00875a}Envelope Icon should appear on upper right corner of portal for clear visibility to user, this way a user is not scrolling down to locate. Usually three lines next to user name is shown and user clicks on it where options are available to choose from (Messages, Profile, Log Out etc) *
ISERVE-185 | Story | ISERVE-42 | Messaging: 2a. User Specified Storage Preferences | As a Client, I want to be able to specify archival / storage preferences for my emails so I can keep my messages organized. ToDo: * Determine what are these storage preferences the user can specify? * {color:#ff0000}GK - Unread, read, sent and deleted with a limited time to archive and limited storage space. Kept very simple. Mickey - Scenario: Client selects Message Center: * Client selects Inbox - ** Inbox headings *** Date *** Case/Program Number *** From *** Subject **** Capability to sort ascending/descending each inbox heading **** Client selects message to read **** Client options ***** Reply, Delete, Back to Inbox ****** notice also posted that messages will be deleted or archived automatically after 90 days * Client selects Sent ** History can be viewed *** Client can select a sent email to read **** Client can Delete or Back to Sent ***** Notice also posted that messages will be deleted or archived automatically after 90 days * Client selects Compose ** Drop down with contact options (assigned worker name, Andi Center, Help Desk) ** Subject - Client enters subject matter or a drop down could be added for options (income, resources etc) ** Body - where client writes message ** Attachment - client uploads documents *** Client Clicks send message **** Pop up "your message has been sent please allow 24 hours for a response" **** Back to Message Center
ISERVE-49 | Story | ISERVE-42 | iServe Content: DHHS Alerts in Banner | As a site visitor, I can receive and see identified DHHS alerts on the home page banner so that I stay current on important information. This section/link must meet iServe design criteria. *Scenarios:* 1. Site visitor views active alerts 2. DHHS staff (IT or Marketing?) manages alerts 2a. Can add new alerts 2b. Can assign publish dates to activate/deactivate based on dates 2c. Can remove alerts 2d. Can assign priority to alerts so it can be ranked accordingly Options: DHHS Alerts in Banner DHHS Alerts in icon messaging (lower priority) This story covers Alerts on iServe and combines ISERVE-50 and ISERVE-51 which have been cancelled.
ISERVE-26 | Story | ISERVE-42 | Messaging: 3ci. Attach Save Electronic Files | As a DHHS Client, I want to be able access my saved electronic files and associate them with a message to provide necessary documentation to DHHS. Process Flow: !image-2021-01-05-19-25-58-692.png! +*ToDo:*+ * Screen Mockup +*Open Questions:*+ * Is there a limit to number of attachments? {color:#FF0000}GK - I can think of no limit that would be needed. Hopefully multi page documents would come as one attachment.
ISERVE-25 | Story | ISERVE-42 | Messaging: 3. iServe NE Portal Account User to DHHS | As a DHHS Client, I want to be able to send secure messages to one or more other iServe Nebraska Portal users or groups of users so I can get my questions answered or provide feedback. Process Flow: !image-2021-01-05-19-15-57-214.png! If user decides to add file attachment see ISERVE-26 otherwise user can send message. ToDo: * Screen Mockup Needed * How are message recipients determined - directory look up, etc. {color:#403294}Nicole - There should be an address book with limited options, such as their specific assigned worker (if they have one) or a general EA or MLTC email/account where these can go to and be pulled from a queue. I don't think they should have access to many recipients as it is likely they may send messages to the wrong person and have to continuously be rerouted to the right person. {color:#ff0000}GK - A directory with only specific, limited options. * Any controls on recipients? * {color:#403294}Nicole - See my above comment as this is addressed. * {color:#ff0000}GK - There should be some type of control so "wrong numbers" aren't dialed. * Message Content text only? Editing controls? * {color:#403294}Nicole - They should be able to submit images or file uploads to upload any documentation that they agency may need or they want to provide. * Auto save draft..timing? * {color:#403294}Nicole - I think this would be a good option as it'll allow the information to be saved incase something happens and the program gets closed out without the message being sent. Every 30 second to one minute is a good. * {color:#ff0000}GK - I would not think this necessary. Allow for manual saving only.
ISERVE-657 | Story | ISERVE-41 | SNAP EBT Card Request | As an applicant applying for SNAP, I want to request an EBT card so that I can purchase food. Per guide: When to request a replacement EBT card: At time of application (initial or recertification), when client declares they do not have an EBT card. If client answers the question on the application and declares they do not have an EBT card, a replacement must be requested when application is pulled from the EA Processing queue and being reviewed. {color:#FF0000}MD - question should remain on the application for the client to answer
ISERVE-638 | Story | ISERVE-41 | Online Application Redirect to FFM | As an application applying for Medicaid who does not need help paying for health coverage, I want my application to route to the federal marketplace (FFM) for eligibility and enrollment in healthcare. Pain Point: There is a question on the ACCESSNebraska application asking the applicant if they need help paying for health care and if they answer "NO" their online Medicaid application is routed to the federal marketplace. The pdf is generated but the application is not in N-FOCUS. If the FFM reaches out to DHHS to say the applicant should be managed by DHHS not FFM then our internal workers can't find the applicant in N-FOCUS. Note: The question on the online app then had help wording added to assist in clarifying the question to the applicant and that was not included in SPA approval as a difference on the original streamlined application that was approved.
ISERVE-575 | Story | ISERVE-41 | Interim Social Security Number | As an applicant, I want the ability to submit my application without an SSN and have the system generate an interim SSN for my unique identification within the system. * Would like the ability to displace/disclose this interim SSN to the individual after generation. * This is currently available in Access NE. Clarify the current tool. Expand description for UI Label and look/feel. *
ISERVE-574 | Story | ISERVE-41 | Applicant Address | As an applicant applying for DHHS benefits, I want to specify my residential address so that I can quickly receive benefit determination. BV was determined including mailing address as well Information to Collect: Residential Street Address: Address Line 2: City: State: ZipCode: {color:#de350b}KJA - {color:#de350b}The EA Application asks for living arrangement and facility or shelter name in the address information section. I like that this information is asked up front and I would think it would be allowable for all programs. {color:#de350b}No home address checkbox (only mailing address fields will populate if checked) - the MLTC application currently has this _after_ the physical address fields. I like this, however, I think it would make more sense to have it _before_. _{color:#de350b}*Physical address fields* _ {color:#de350b}Street address {color:#de350b}Apt or Suite Number {color:#de350b}Does anyone need to be listed as the "In Care Of (c/o)"? Yes / No {color:#de350b} (If Yes) List Person or Organization field populates {color:#de350b}City {color:#de350b}State {color:#de350b}Zip Code / Zip + 4 {color:#de350b}County {color:#de350b}Is your mailing address the same as your physical address? Yes / No {color:#de350b} (If no is checked, mailing address fields populate) _{color:#de350b}*Mailing address fields* _ {color:#de350b}PO Box or {color:#de350b}Street address {color:#de350b}Apt or Suite Number {color:#de350b}Does anyone need to be listed as the "In Care Of (c/o)"? {color:#de350b} (If Yes) List Person or Organization {color:#de350b}City {color:#de350b}State {color:#de350b}Zip Code / Zip + 4 {color:#de350b}County {color:#de350b}The EA Application only also asks for previous address information (Address Lines 1, 2 & 3, City, State, Zip). {color:#de350b}I'm not sure why this is asked and Kristi wasn't sure either, but the reasoning may be as a possible lead to assistance being received in another state (though information regarding assistance received from another state is asked in the household section of the online app / page 5 of the EA-117). {color:#de350b}I added screen shots of each type of application as well the NF Address window, a comparison spreadsheet of the 3 applications and information regarding the NFOCUS address windows. If we are feeding the address information into NF, do we need to duplicate these fields on the application or will we be using something like the NT Address window in NFOCUS (currently grayed out) where the address will be pulled into? (See attached screen shot of NF Address window.)
ISERVE-577 | Story | ISERVE-41 | Define relationships between members on application | As an applicant, I want to specify relationship information between persons being added to the application and the main applicant/head of household so that benefits can be established appropriately. Add List of relationship types...
ISERVE-576 | Story | ISERVE-41 | Designate Head of Household | As an applicant, I want to specify who is designated as head of household so I the right person can manage the benefits.
ISERVE-567 | Story | ISERVE-41 | IE Application: Specify Authorized Representative(s) Role | As an applicant, I want to specify the role my identified authorized representative(s) (e.g., parent / legal guardians, application assistance providers) can have on my behalf so I can secure the proper control. Authorized Representative Roles: * Make application and report changes for the household * Use EBT card Note: The authorized representative for obtaining benefits may or may not be the same individual designated as an authorized representative for the application process or for meeting reporting requirements. {color:#ff0000}KJA - Just to clarify, a guardian is a person or institution appointed by a judge to take care of and be legally accountable for a person who cannot take care of himself or herself (ward). Wards are either minor children or incapacitated persons. A guardian has the power to apply for benefits for the ward and give necessary consent, approval and releases on their behalf. A ward would not specify roles that a guardian can have on their behalf. A guardian can name someone else as an Authorized Representative for the case. {color:#ff0000}I've added a copy of the MLTC-35 Designation of Authorized Representative form to attachments. {color:#ff0000}Scopes of authorization included on the form are: * {color:#ff0000}Sign an application on the applicant €™s behalf * {color:#ff0000}Complete and submit a renewal form * {color:#ff0000}Receive copies of the applicant or beneficiary €™s notices and other communications from the agency * {color:#ff0000}Act on behalf of the applicant or beneficiary in all other matters with the agency
ISERVE-564 | Story | ISERVE-41 | Expedited IE application (SNAP) | This story will go 1 of two ways...waiting on feedback: As an applicant, I want my application(SNAP) expedited because of crisis so that I can receive assistance immediately. OR (tech enabler) When an application comes in with these responses:... then flag the application as high priority in N-FOCUS so the program is pend/tied first.
ISERVE-568 | Story | ISERVE-41 | Earned Income | As an applicant, I want to specify my earned income data so that I can have benefit eligibility determined quickly. Data to Capture: * Gross total earned income for the Head of Household(HH) {color:#FF0000}(Ability to add hourly wage, hours worked, how often paid) * Gross earned income by HH member {color:#FF0000}(Ability to add hourly wage, hours worked, how often paid) * Source(s) of earned income {color:#FF0000}(Type of income drop down box for multiple entries per person) * Self-Employment earned income by HH member {color:#FF0000}(past 3 months) * Self-Employment Expenses (Allowed/Disallowed) or Self-Employment expense standard (if state has one) {color:#FF0000}(past 3 months and description of each expense) * Net losses from farm self-employment * Frequency of earned income
ISERVE-560 | Story | ISERVE-41 | Application Date | As an applicant, I want my application date to be recorded appropriately so that I can not only receive timely benefits but I can not also qualify for retro benefits when applicable. Medicaid: {color:#ff0000}KJA - Medicaid apps have a Submit/Received date of actual time stamp. {color:#ff0000}The current online application captures the start date, the submit date and the received date. Economic Assistance (including SNAP): {color:#ff0000}KJA - The application is received the day it is submitted using the electronic signature or the next business day if submitted after hours (5:00 PM CST) or on a weekend or holiday. Processing begins the day the application is received. {color:#ff0000}The current online application captures the request date, the submit date and the received date. DD - Notes: * This is traceable to SIRT Compliance.
ISERVE-563 | Story | ISERVE-41 | Unlimited Household Members and Information | As an applicant, I need to add 1 to many household members when I am applying for SNAP using the multi-benefit application. Data to Include: * First Name (Required) * MI * Last Name (Required) * SSN (Optional) * Date of Birth (DOB) * Do they purchase and prepare food with you (Y/N) * {color:#FF0000}Sex
ISERVE-554 | Story | ISERVE-41 | IE Application: Applicant leaves additional Comments on an Application | As an Applicant, I want to be able to submit Comments about my household situation on the applications so that the Case workers can consider additional details during my program eligibility process. _+*Scenario*+_ : Applicant leaves comments with valid data *Given* that the applicant is in a role of logged in or Guest user *AND* is completing a Multi-Benefit application *When* the applicant navigates to the section of "Is there anything else you would like to tell us?" *Then* the system should show a "Text box" to enter the comments/notes *When* the applicant enters the comment *AND* clicks a "Save" or "Submit" button or Exits the Text Box *Then* the system saves the comment *AND* the system displays the comment *AND* the system shows "Remove" or "Edit" icons below the comment to enable an Applicant Delete and Change comments. //Need to check Requirement * Reasonable Character Limit for a Comment field based on technical limitations. * This Form field will be Labeled "_Optional_"
ISERVE-518 | Story | ISERVE-41 | IE Application: 14. System Validation Check | If the System determines that the information entered by the Applicant is either invalid or is not verified by internal or external data sources: a. The System flags the field and displays the reason for the information field error. b. The System prompts the Applicant to re-enter information.
ISERVE-519 | Story | ISERVE-41 | IE Application: 18. Systematic Program Requirements Compliance Check | System determines if the applicant needs to comply with DHHS program requirements. Several DHHS programs require that the Applicants agree to comply with other DHHS program requirements (e.g. CSE)
ISERVE-504 | Story | ISERVE-41 | IE Application: 5. DHHS Program Selection | As an applicant, I want to select the programs options I wish to apply for, so that I can complete the proper information needed to quickly receive program benefits. An applicant can: * Select health coverage only application *This is a regulation requirement * Select one or more programs ** {color:#ff0000}Applicant selects two programs from a list (Snap, Medicaid) - MD *** {color:#ff0000}Systems populates all the questions needed for both programs selected ** {color:#ff0000}Applicant selects one program from a list (Snap) - MD *** {color:#ff0000}Systems populates all the questions needed for that specific program * Select all programs ** {color:#0747a6}KJA - They should be able to select as many programs as they want to apply for, however, they should not be given a separate "Select all programs" option. It would cause a lot of extra work to deny programs which they are obviously not eligible for (Ex. a person that does not pay utilities would not need to apply for LIHEAP) (Nicole & Kristi - Agreed that applicants should not be able to "Select All" as stated above, almost all applicants would not be eligible for all programs and causes unnecessary work for the workers to deny apps. They should select the programs for which they want to apply for) ** An explanation of each program should be included so they know exactly what they are applying for ** {color:#57d9a3}Nicole & Kristi - Explanation of what the program is would be good, but it should very simplistic on requirements if those are going to be included as qualifications are different for each person and a worker would be the one to go over those. (Example: ADC - Is there a child in the HH or LIHEAP - Are you responsible for paying heating or cooling?) *** {color:#ff0000}Description of the program and a synopsis of the basic requirements to qualify for that program - MD Programs to include: * Medicaid * EA (Should this be broken out into SNAP, LIHEAP, ADC/TANF...) ** KJA - Yes, this should be broken out into the separate programs. ** {color:#57d9a3}Nicole & Kristi - Each program should be listed separately because it if is combined as EA, all programs would have to be pending and addressed (approved or denied) regardless if they just meant to apply for one. Also, not all clients understand what programs fall under which category. * DD Note: There is debate in having this step at all. We want to: 1) Cover more programs with a single application and not limit coverage by not having the applicant apply to all; * {color:#ff0000}MD - As mentioned above there should be a description and synopsis of basic qualifying requirements for each program * {color:#ff0000}MD - Should be a drop down box or check box to select the programs the client is interested applying for ** {color:#ff0000}Something else to consider if they select LIHEAP they would be asked some basic questions to determine potential eligibility before the request can be submitted, if applicant does not qualify under basic the questions they would not be able to apply. *** {color:#ff0000}I see that Nicole and Kristi addressed the second point here, as we would never not allow a client to apply. I'll add, the point of benefit discovery is to have as few questions as possible and to be as inclusive as possible. We will not be adding any questions with the intent to disqualify someone nor will this be decided within Benefit Discovery. ** {color:#ff0000}Nicole & Kristi - In regards to the comment above, LIHEAP is a complex program and basic questions would not be able to determine eligibility so I don't think these questions need to be asked during program selection. This is something a worker will have to discuss with the client. Also, they have a legal right to apply for any program they want regardless if they would qualify or not. 2) Meet CMS guidelines 3) Allow applicants choice over accepting program benefits. * MD - In my opinion if the client is applying for the programs they are already wanting the programs. However, in some cases circumstances may change in the applicants HH and therefore they may not want the benefits any longer. If the option was there for the client to accept the final determination of approval would be a nice addition to offer them. This could also help with eliminating people receiving benefits and having to collect for over payment.
ISERVE-506 | Story | ISERVE-41 | IE Application: 9. Applicant Enters Economic Assistance Information | As an applicant, I want to enter information relating to Economic Assistance Benefits and Services so that I can receive a fast determination. In Scope: * SNAP * ADC/TANF * LIHEAP * AABD * CC * SSAD * SSCF * RRP * SDP * Emergency Assistance
ISERVE-505 | Story | ISERVE-41 | IE Application: 9. Applicant Enters Health Related Details | As an applicant, I want to enter information related to Medicaid enrollment so I can receive a fast determination of benefits. In Scope: * Medicaid * CHIP * Medicaid Expansion
ISERVE-497 | Story | ISERVE-41 | Application Draft Available Timeline | As an iServe Nebraska Portal administrator, I want to be able to configure the time allowed to use a previously started draft IE Application and I would like that default time set to 30 days.
ISERVE-336 | Story | ISERVE-41 | IE Application: Identify Authorized Representative(s) | As an applicant, I want to include authorized representative(s) (e.g., parent / legal guardians, application assistance providers) on my integrated eligibility application so that I can have help when needed. Authorized Representative Data to Capture: * First Name * MI * Last Name * Street Address * Street Address Line 2 * City * State * Zip Code * Telephone Number
ISERVE-308 | Story | ISERVE-41 | IE Application- Preferred methods of communication | [~rebecca.peplinski]-- *At this time, clients will always receive a copy of their IE application in Medicaid through the mail, regardless of user selected preferences. * Erin Noble with Policy states that this MAY be so that the client has proof of what has been submitted so that a client can make necessary changes * Clients can sign the application indicating that something has changed ** There MAY not be a policy requirement for this ** Email has been sent to Alvin Zimmerman and Michelle Eby for clarification As an applicant, I would like to be communicated in my preferred method of communication.- Absolutely Is this needed for MVP if only for phone applications? Circle back Acceptance Criteria * As an applicant, I would like to not receive mail from DHHS if this is not my chosen preference * As an applicant, I would like to receive communication through my chosen preferences
ISERVE-309 | Story | ISERVE-41 | IE Application Quick Submit: Submit Application with Minimal Input | As an applicant, I would like the option to submit an integrated eligibility application with only my name, address, and electronic signature (the essential entries in order to make the application valid).
ISERVE-296 | Story | ISERVE-41 | IE Application: Legal Screener Questions | As an IE applicant, I need to validate that the information provided is accurate and correct before submitting my application. Signature Page Wording for online application is attached Signature Page Wording for paper application is attached In addition added: Rights and Responsibilities and Notice of Information Privacy Practices both are these are attached to the online renewal form.
ISERVE-279 | Story | ISERVE-41 | IE Application: 4. Integrated Eligibility (IE) Application Options(New/Draft) | As a DHHS applicant with an iServe Nebraska account, I want to be presented with options to start a New IE application or continue an existing IE Application so that I can apply for benefits.
ISERVE-274 | Story | ISERVE-41 | IE Application: 13. Applicant Provides Contact Preferences | As an applicant, I want to enter contact information so that I can be reached regarding my application for healthcare/ assistance. To-Do: * List out information to collect (ie. Name, Address, etc) * Add acceptance criteria * Determine required fields * Determine validation (text length, type of values) _(Applicable fields should auto populate from account information already on file with the ability for the applicant to make any needed changes.)_ *Please review your contact information below and update as needed.* +First Name+: _current max of 20 characters / *required field_ +Middle Name+: _current max of 20 characters_ +Last Name+: _current max of 25 characters / *required field_ +Suffix+: _<<select>> w/ drop down arrow to select from: I / II / III/ IV / JR / SR / V_ +Date of Birth+: _limited to numbers only and be in the mm-dd-yyyy format; calendar to choose date from should be included; the hyphens should auto populate so that the applicant only needs to enter the numbers; must contain exactly 8 numbers; must be in the past_ + €œNo home address € with checkbox+ - _if checked, only the mailing address fields only should appear along with additional checkbox -_ + €œI need my mail sent to General Delivery € with checkbox+. _If this is checked, €œGeneral Delivery € should be populated to the Street Address field of the mailing address and a message to_ €œPlease provide the City, State and Zip code for General Delivery. € +Street address+: _current max of 50 characters / *required field unless it is provided in the mailing address section_ +Apartment or suite number+: _current max of 50 characters_ +Zip Code+: 5 _digit field / must contain numbers only and exactly 5 numbers + 4 digit field / must contain numbers only and exactly 4 numbers /*5 digit field is required unless it is provided in the mailing address_ +City+: _should auto populate if possible when the zip code is entered or choices provided if more than one town associated with that zip code /max of 25 characters / *required field unless it is provided in the mailing address_ +State+ €“ _should auto populate when the zip code is entered if possible; <<Select>> with dropdown arrow to select from all US STATES & TERRITORIES + DISTRICT OF COLUMBIA / *required field unless it is provided in the mailing address_ +County+: _should auto populate when a NE zip code was previously entered; <<select>> with a dropdown of names of all counties in NE listed_ + €œIs your mailing address the same as your home address? € €˜Yes €™ & €˜No €™ radio buttons+ _If no is checked, the mailing address fields should populate._ +Street Address or PO Box:+ _current max of 50 characters_ +Apartment or suite number+: +_current max of 50 characters_+ +Zip Code+: 5 _digit field / must contain numbers only and exactly 5 numbers + 4 digit field / must contain numbers only and exactly 4 numbers_ +City+: _should auto populate if possible when the zip code is entered or choices provided if more than one town associated with that zip code - at a minimum for NE zip codes_ _/ current max of 25 characters_ +State+: s_hould auto populate when the zip code is entered if possible - at a minimum for Nebraska zip codes; <<Select>> with dropdown arrow to select from all US STATES & TERRITORIES + DISTRICT OF COLUMBIA_ +County+: _should auto populate when a NE zip code was previously entered; <<select>> with a dropdown of names of all counties in NE listed_ €œ+Does your mail need to be sent €˜In Care Of €™ (c/o) someone else? € €˜Yes €™ & €˜No €™ radio buttons _(_+_If yes, C/O field should then populate.)_ +Phone number+: _include example text €œExample: (999)999-9999 € / user should be able to enter numbers only with the ( )- characters auto populating / must contain exactly 10 numbers_ +Extension+: _limited to numbers / current max of 6 characters_ +Phone type+: _<<select>> with dropdown to choose from Cell Phone; Home; Work; Message Phone Only; TTY/TDD_ +Second phone number+: _include example text €œExample: (999)999-9999 / user should be able to enter numbers only with the ( )- characters auto populating / must contain exactly 10 numbers_ +Extension+: _limited to numbers / current max of 6 characters_ +Phone type+: _<<select>> with dropdown to choose from €˜Cell Phone; Home; Work; Message Phone Only; TTY/TDD €™_ +Preferred spoken language+: _default to English with dropdown of language choices_ +Preferred written language+: _default to English with dropdown of language choices_ +Email Address+: _current max of 36 characters_
ISERVE-276 | Story | ISERVE-41 | IE Application: 18b. Issue Application Denial Notice | As an IE applicant, upon notification of additional DHHS program requirement , applicant denies the compliance. Applicant does not comply with the program requirements * If does not comply then system issues application denial notice and ends the IE Application process. *{color:#de350b}Mickey - Compliance is part of the signature process, if a client does not comply then they are not able to sign the application. A pop up should populate if the client does not check the box that they comply with program requirements this should be for both EA and MLTC * {color:#de350b}*Screen Mockup - example in attachments so when they click on I agree to comply a pop up window will display the verbiage of the program requirements.* {color:#de350b}*Verbiage* *{color:#de350b}- By not agreeing to the program requirements your application is denied * {color:#de350b}*When the applicant has filled out all the pertinent information on the application, the submit button will trigger the compliance verbiage and require the client to accept it or deny it* {color:#0747a6}KJA - Added examples from current online apps for both MLTC & MA. Requirements do vary from program to program. There is no "automatic" denial notice sent by the system at this time. I think this would need to be discussed with all applicable Legal Departments. ? SME team has questions regarding this story
ISERVE-273 | Story | ISERVE-41 | IE Application Exit: Applicant Discards IE Application | As an applicant, I want discard my Integrated Eligibility application and not have it saved. Mickey - Add 3 scenarios Scenario 1 * Begin application process * Client exits unfinished application * Pop up appears "Do you wish to save application?" ** No ** Application not saved Scenario 2 * Application is completed * Client does not choose submit and exits * Pop up appears "Do you wish to save application?" ** No ** Application is not saved Scenario 3 * Application has completed and saved application * Applicant has access to submitted applications * Applicant views applications * Application has choice to delete applications * Confirmation message pops up "Are you sure you want to delete application?" * Applicant says yes, application is deleted
ISERVE-275 | Story | ISERVE-41 | IE Application: 17. Applicant Release Authorization | As an IE applicant, The Applicant authorizes a release of information to DHHS.. Screen Mockup Wording of Privacy Practice Mickey - added to attachments KJA - Added screen shots from ACCESSNebraska + Rights & Responsibilities
ISERVE-271 | Story | ISERVE-41 | IE Application: 7a. Applicant Does NOT Give Consent to 3rd party lookup | As an applicant, I do not want to give my consent to DHHS to allow data lookups via internal and external (3rd party) applications in order to populate data into my application. -- System should ask the applicant if they are sure they do not want to consent and let them know by doing so their application will be withdrawn --System should withdrawl the application -- System should notify the application of the withdrawl
ISERVE-270 | Story | ISERVE-41 | IE Application: 4b. Continue Saved Draft Integrated Eligibility (IE) Application | As a DHHS applicant with an iServe Nebraska account, I want to be presented with my draft application(s) so that I can continue to apply for benefits.
ISERVE-148 | Story | ISERVE-41 | IE Application: 21. Interview Notification | As an applicant for SNAP and/or Childcare Subsidy, I want to be notified if I need to complete an interview and be provided with information to quickly conduct the interview so I can speed up my access to benefits.
ISERVE-147 | Story | ISERVE-41 | IE Application: 18a. Applicant acceptance of Program Requirements Compliance Check | As an IE applicant, I need to be notified if there is an additional DHHS program requirement that calls for my compliance of this set of program requirements so that I can accept / deny the compliance. To Do: * Screen Mockup * Need Wording of [Comply with Program Requirements]-- does this vary? * Need Wording of Denial Notice due to non-compliance of program requirements * Details needed on what triggers applicant to need to agree to comply with other DHHS program requirements. +Workflow:+ Applicant either accepts compliance (IE Workflow continues with electronic signature story) OR Applicant does not comply with the program requirements * If does not comply then system issues application denial notice and ends the IE Application process. *{color:#de350b}Mickey - Compliance is part of the signature process, if a client does not comply then they are not able to sign the application. A pop up should populate if the client does not check the box that they comply with program requirements this should be for both EA and MLTC * {color:#de350b}*Screen Mockup - example in attachments so when they click on I agree to comply a pop up window will display the verbiage of the program requirements.* {color:#de350b}*Verbiage* *{color:#de350b}- By not agreeing to the program requirements your application is denied * {color:#de350b}*When the applicant has filled out all the pertinent information on the application, the submit button will trigger the compliance verbiage and require the client to accept it or deny it* {color:#0747a6}KJA - Added examples from current online apps for both MLTC & MA. Requirements do vary from program to program. There is no "automatic" denial notice sent by the system at this time. I think this would need to be discussed with all applicable Legal Departments.
ISERVE-145 | Story | ISERVE-41 | IE Application: 13. Contact Preference Check | System validates applicant has contact preferences in their Portal user profile.
ISERVE-144 | Story | ISERVE-41 | IE Application: 12. Applicant Submits Integrated Eligibility (IE) Application | As an integrated eligibility applicant, I want to submit my completed application to NE DHHS so that I can officially apply for benefit programs. Screen Mockup: Notification Message after submission? {color:#ff0000}Nicole - The notification message should be something simple and understandable. (Ex. You have successfully submitted your application) Included in the message should be a box with options - Log Out/Exit or Return to Main Menu. Any other details on what to expect next? €“ information for applicant? {color:#ff0000}Nicole - As most applications would need an interview, there should be a notification message, as we talked about, informing them to call Access Nebraska to complete an interview or provide an option for them to schedule and interview for a time that works for them within the timeframe that the application needs to be processed. Note: Between [Submit] and [notification] there is a story for data validation and contact preferences.
ISERVE-150 | Story | ISERVE-41 | IE Application: 15. Applicant Marks IE Application Complete | As an IE Applicant, I want my IE Application to process immediately upon completing all IE application processes. {color:#FF0000}Nicole - If a client submits an application with all information provided and the system could verify all the needed information with interfaces and other sources, then the system should be able to process the application and provide benefits to the client. GK - As a staff member, I want the basic information filled out by the applicant automatically entered into and verified by the system. To Do: * Screen Mock up * Notifications? * Back End Processing with N-Focus or other internal systems? WHat systems. What data elements, batch processing or real time? REplace the pdf process with integrated back-end processes (API)
ISERVE-142 | Story | ISERVE-41 | IE Application Exit: Applicant Saves Draft IE Application | As an iServe Nebraska Portal user, I want my Integrated Eligibility application to save periodically (e.g. every 1 minute) so that I do not lose any information entered. Details: How often {color:#ff0000}As an applicant, I would like the application to automatically save every 60 seconds. Display Notification when saving that reads " €“ get this wording from SMEs" {color:#ff0000}As an applicant, I would like the wording for saved information on an application to state, "Saved - Last updated # seconds ago." Determine where notification should appear {color:#ff0000}As as applicant, I would like to see the saved notification at the bottom of the screen alongside the "Next/Continue" button.
ISERVE-141 | Story | ISERVE-41 | IE Application: 10. Applicant Revises PrePopulated Fields | As an applicant, I want to validate/updated prefilled data so that I can be sure my application has the most up to date information prior to submitting.
ISERVE-146 | Story | ISERVE-41 | IE Application: 16. Privacy Practice Notice | As an IE applicant, I need to be notified of DHHS's notice of privacy practices so that I can authorize the release of my information to DHHS. Possible Wording: I affirm and certify that all the information and answers to questions herein are complete, true and correct to the best of my knowledge and belief. Mickey - Authorization for Release of Information on application currently reads as follows: I authorize the release of information requested by DHHS. The requested information will be used solely in the administration of public assistance programs and will not be released to any other person or agency outside DHHS. I understand DHHS may release information to another agency when the services of that agency have been requested or when the objective in obtaining the information is to provide the service to me or any member of the assistance unit. Screen Mockup Wording of Privacy Practice - Full wording is in the attachment
ISERVE-143 | Story | ISERVE-41 | IE Application Exit: Applicant Leaves Application | As an integrated eligibility applicant, I want to be able to leave the integrated eligibility application and decide if I want to save or discard the current application. Details: Screen mockup? * Client starts application ** Client clicks exit *** Pop up "Do you wish to save your application?" **** Yes ***** Systems Pop up "Your information has been saved." ***** Systems redirects client to home screen *** Client attempts to leave the site **** Pop up "Are you sure you want to exit?" ***** Yes ***** Pop up "Do you want to save your information?" ***** Yes ***** Pop up "Your information has been saved, you are being redirected to the log on screen" ***** Redirect client to log on screen **** Pop up "Are you sure you want to exit?" ***** Yes ***** Pop Up "Do you want to save your information?" ***** No ***** Pop Up "You are being redirected to the log on" ***** Redirect client to log on screen Workflow: Applicant chooses to leave but save the application Applicant chooses to leave and discard the application Open question €“ decision needed: When applicant leaves should system go to log out or back to home page? Process flow from procurement directs to log out. {color:#ff0000}GK - It should go to log out with the option of returning to home page to start over.
ISERVE-140 | Story | ISERVE-41 | IE Application: 7b. Applicant System Identity Check | Identify the applicant against existing system identifiers to confirm identity Process Flow - If system is not able to match data to the applicant system prompts applicant for identity info: Option 1 €“ data is entered(what info?) €“ retries to identity match. Option 2 - applicant does not enter data - continues to blank application
ISERVE-75 | Story | ISERVE-41 | IE Application: 6a. Client Benefit Enrollment Display | As an applicant, I want to: 1) See what programs I am already enrolled in; 2) the end date of that enrollment; 3) information about how to apply for renewal/redetermination to the DHHS Program so I can understand my existing Benefits Enrollment. In Scope Benefits: * Medicaid * PAS * CHIP * SNAP * ADC/TANF * LIHEAP * AABD * CC * SSAD * SSCF * RRP * SDP * Emergency Assistance
ISERVE-74 | Story | ISERVE-41 | IE Application with Assistance: Applicant Contacts DHHS | As an iServe Nebraska applicant, I need timely assistance so I can submit an Integrated Eligibility application.
ISERVE-73 | Story | ISERVE-41 | IE Application: 4a. Start New Integrated Eligibility (IE) Application | As an iServe NE applicant with an iServe Nebraska account, I want to start a "New" IE application so that I can apply for benefits.
ISERVE-62 | Story | ISERVE-41 | IE Application: 11. Real-time data validation | As an iServe Nebraska applicant, I want information I enter to be quickly validated in real-time so that I can complete my application quickly and have more success in submitting the application.
ISERVE-66 | Story | ISERVE-41 | IE Application: 6. Client Benefit Enrollment Check | Technical check between iServe and N-FOCUS on a new applicant for existing active DHHS benefits for use in ISERVE-75 UI display. * Medicaid * ADP/TANF * LIHEAP * SNAP
ISERVE-65 | Story | ISERVE-41 | IE Application: 3a. Create Account | As an iServe Nebraska applicant without an existing account, I want to create an account login prior to starting my IE Application so that my information entered is associated to my account.
ISERVE-64 | Story | ISERVE-41 | IE Application: 3b. Log in to existing iServe NE Account | As an applicant, I want to login to my account prior to starting my IE Application so that my information entered is associated to my account.
ISERVE-48 | Story | ISERVE-41 | IE Application: 8. PrePopulate Application Fields | As an applicant, I want my known information from DHHS and external sites to pull into my Integrated Eligibility application so that I do not have to reenter information. * Benefit Discovery * Existing Client (N-FOCUS) * Prior Client (N-FOCUS) * External Systems
ISERVE-21 | Story | ISERVE-41 | IE Application Supplemental Information: Applicant uploads previously saved documents | As an integrated eligibility applicant, I want to access my saved electronic files so that I can attach them to my application for benefits and services. Scope: This story is specific to associating attachments already saved to an iServe Nebraska account to an IE application during the IE Application Process. Process Flow: * User selects ability to upload files * System provides ability to select one or more files associated to user's iServe Nebraska account * User selects files from existing account * User associates files with IE Application * System displays message confirming the files have been associated to the IE Application * System provides notification to DHHS staff that uploaded files have been associated with IE application ToDo: * Process Flow above needs reviewed/confirmed * Screen Mockup - how does user interact with UI to associate files * Identify technical constraints size/number of files eligible for associating to IE application * Identify wording of notifications/messages in above Process Flow
ISERVE-20 | Story | ISERVE-41 | IE Application: 9. Applicant Enters Common Information | As an applicant, I want to enter information to begin an application for benefits so that I can quickly get a determination of benefits.
ISERVE-30 | Story | ISERVE-41 | IE Application: 7. Applicant Consent to 3rd party lookup | As a applicant, I want to understand my rights regarding consent and 3rd party application data so I can give my consent to DHHS to allow data lookups via internal and external (3rd party) applications in order to populate data into my Integrated Eligibility application.
ISERVE-31 | Story | ISERVE-41 | IE Application: 19. Electronic Signature | As an IE Applicant, I want to electronically sign my Integrated Eligibility Application for ease of applying with my official signature. To Do: * Is the application for a single signature or more than 1 * Different if signing for someone else (parent of minor, someone acting on behalf of someone else) Applications can be signed by: €¢ Applicant €¢ Non-applicant in applicant €™s family or household €¢ Someone acting responsibly for a minor or person incapacitated €¢ An authorized representative, as designated
ISERVE-587 | Story | ISERVE-11 | SPIKE - Research options for offering single login experience (MVP)
ISERVE-534 | Story | ISERVE-11 | IAM: 9. New User: Enter Contact Preferences | As a new iServe Nebraska Portal user, I want to provide my communications preferences so I know how DHHS will reach me. * Preferred Method of Communication (Required) ** Options: email, text, phone, or mail ** Text requires at least one other option to be selected * Preferred Method of Communication can be selected at the time of new account creation * Preferred Method of Communication can be selected at any time through editing account details * The system should present in the preferred language of the user if selected, or in the default system language * Help content is available to user to explain the preferred method of communication values * Details should be sent to N-FOCUS and stored on the user's profile +Workflow+: * User selects System communication preferences * System saves user selected communication preferences
ISERVE-533 | Story | ISERVE-11 | IAM: 5. Username Verification configuration | Establish a configurable period of time for account verification. 5. The System saves the unverified username for a configurable period of time What is the default? 24 hours? {color:#4c9aff}Outstanding Questions * {color:#4c9aff}What happens when the verification period duration is updated and account verifications are in progress? Do they follow the historical verification duration or new? (e.g. Are we tracking history) +*Feature*+: New accounts must go through a verification process +Scenario+: Pending Verification *Given* a new user has created an account *When* the new user clicks submits *Then* the system pends the account for verification period. +Scenario+: Update Verification Period *Given* a system admin wants to change the account verification period *When* the timeframe value has changed *Then* all future account verifications will follow the new verification period. +Scenario+: Unverified Account *Given* a new user creates an account *And* the new user does not verify the account *When* the verification period has elapsed *Then* the new account is deactivated. +Scenario+: Late Verification *Given* a new user creates an account *And* verification period has elapsed *When* the user attempts to verify *Then* the user receives an error message *And* the account is not verified. +Scenario+: Account Verified *Given* a new user creates an account *When* the user verifies the account *Then* the account status is set to active *And* the account is marked as verified
ISERVE-532 | Story | ISERVE-11 | IAM: 4b. Establish Account Verification Options | As a user, I want to choose an option to verify my account creation so I can confirm my account setup. * Account verification is required before a user can log into the account * An application can be submitted by the user before verification, but only at the time of account creation * Options include but are not limited to: * Phone * Text * Email Based on selected verification method, associated details must have been entered on the account details. {color:#4c9aff}Outstanding Questions * {color:#4c9aff}Can this verification method differ from the preferred communication method for the user? * {color:#4c9aff}Is there a need for a method beyond verification via Phone, Text, or Email? * {color:#4c9aff}Do we pause the next step after account creation until verification is complete? For example, if creating an account before submitting the multi-benefit application do we allow the user to proceed or wait until the account is verified?
ISERVE-348 | Story | ISERVE-11 | iServe NE Portal - User log out | As an iServe Nebraska Portal Account holder, I want to log out of the Portal so I know my account is secure upon leaving. * User should have the ability to log-out of their account at any time when they are on the iServe Portal. * Once logout has concluded, the user should be taken to the main landing page for the site * Notification should be given to the user that logout has been successful * Any cached authentication should be deactivated so the user can no longer see account information.
ISERVE-347 | Story | ISERVE-11 | IAM: 5. Identify Inactive Portal Accounts | As a DHHS iServe Nebraska Portal Account Administrator, I need the ability to identify inactive user Portal Accounts so that we can keep our system's user base accurate and secure. * A €œno activity € report should be available and provide system administrators with a list of all user accounts that have not had any login activity for the prior 15 months. ** Includes current day in count ** Does not factor in the associated cases/benefit programs and their application statuses * User should receive a notification through their preferred contact method that their account has not had activity for 15 months and will be deactivated. ** This is the initial notification that the account will be deactivated ** The notification should include a note that users must log into their account to keep it active ** Example Text: "Your account has been inactive 15 months, if you wish to reactive your account please click the following link" * If the user account is still inactivate 15 months + 3 days (72 hours after first notification), then the account should be deactivated. ** Users should receive notification via preferred contact method that their account has been deactivated ** Users can go through a process in ISERVE-186 to reactivate their account later if desired ** Example Text: "Your account has been deactivated. Please visit the iServe page to login and reactivate your account." * Username should still be associated to the individual so it cannot be duplicated after deactivation.
ISERVE-343 | Story | ISERVE-11 | iServe Portal Account - Recover Username | As an established iServe Nebraska Portal account holder, I want to recover my username when I forget it so that I can log into my existing Portal account. * Log on screen includes an option for "Forgot Username". * This process requires the use of the recovery email address or the primary email address ** There should be an ability for the user to add a recovery email address to their account profile ** This recovery email address is not a required field ** The recovery process should request an email and it must be one of these two * Link to recover username should be sent to user through preferred communication method * User should be prompted to answer security questions and must answer all three security questions correctly * If security questions are answered correctly, then the username information is sent to the preferred communication method on the account. * If there is no associated account or a single account cannot be identified, then user should be prompted on screen to contact help desk with phone number.
ISERVE-344 | Story | ISERVE-11 | iServe Portal Account - Reset Password | As an iServe Nebraska User, I want to be able to reset my account password so that I can access my account when I have forgotten my password. * Requires the user to provide the account username ** Without a username the user must first recover their account username (ISERVE-343) * User is prompted to answer security questions to authenticate they own the account ** Security questions should be answered on the account profile ** There should be 3 total security questions that have been answered by the user when creating the account ** These questions can be updated at any time through editing the account * Once password has been reset, a notification should be sent to the user via their preferred communication method ** Sample Text: €œYour iServe account password has been changed. If this was not done by you, please contact DHHS Support Desk. € * If security questions are not provided, then password reset should trigger a link to the user €™s preferred contact method. * User should have the ability to reset password at any time through account maintenance without the €˜forgot password €™ functionality. ** This method would not require security questions to be answered as the user is already authenticated *Screen Samples:* !image-2021-03-05-15-54-20-231.png! !image-2021-03-05-15-50-14-695.png¦thumbnail!
ISERVE-346 | Story | ISERVE-11 | IAM: Merge Duplicate Portal Accounts | As a DHHS iServe Nebraska Portal Administrator, I need the ability to merge duplicate user Portal Accounts so that we have a single user account per unique identifier. * A monthly report should be generated to compare all active accounts within the iServe system and determine if they are duplicates based on account attributes: ** Name ** Address ** Email ** Phone Number * Output should be available for system administrators to determine how to merge accounts appropriately. * One account should be selected as primary and the others as the secondary/account to be deactivated. * Should be a feature in the system for system administrators to select two accounts that are the same and merge them. * Once account is deactivated through merge, any documentation should be migrated to the new activate account. * Account history should be tracked to note when accounts have been merged and what information has been migrated. * Once an account has been merged it cannot be unmerged.
ISERVE-334 | Story | ISERVE-11 | IAM: 5a. Reverification Option | As an iServe Nebraska user, I want an option to resend account verification so that I can confirm my iServe Nebraska account creation. * If verification is not complete and user attempts to login, user should be prompted to retrigger the verification process. * User should be presented again with the option of verification method (text, phone, email) when attempting to retrigger the verification process. * When triggered, account verification process (ISERVE-532) should be triggered.
ISERVE-331 | Story | ISERVE-11 | IAM: 4. Account Duplication Check | As an iServe Nebraska user, I want to be notified upon creating a new iServe Nebraska account if I already have an existing account. Screen Mockup * Selects create account * Client creates username and password * Client provides email address and recovery email address * Client provides social security number and DOB ** Client submits information for account creation ** System checks to ensure existing information does not currently exist *** System finds account matching information provided *** Pop up appears "You currently have an active account with DHHS, please contact the customer support at ..... ***
ISERVE-333 | Story | ISERVE-11 | Login: User Inactive Timeout | As an iServe Nebraska user, I want to be logged out of my iServe Nebraska account after not being active so that my account can remain secure. * After 5 minutes of being idle on a screen user should receive a warning prompt of inactivity. ** Message: "You are about to be logged out due to inactivity. Select if you wish to remain logged in" * User should be able to select a field allowing them to remain logged in as they are still active. * After 20 seconds of the screen appearing, if no action is taken then the user is automatically logged out of the system * User should be redirected to logout screen showing they have been logged out ** User should be unable to access account/benefit details after logout * System admin role should have the ability to update this time-out duration in the system to increase or decrease when necessary.
ISERVE-186 | Story | ISERVE-11 | IAM: Reactivate Account: By User | Provide the client with the ability to reactivate their iServe account after it has been deactivated. * During account reactivation, the account should be compared with all active accounts based on account attributes. ** Name ** Address ** Email ** Phone Number * If an active account matches account attributes, then user should be prompted they cannot reactivate the account. Examples: Client enters email address on log on page Message pops up that they currently have an inactive account with that email address Would you like to reactive your account? Yes or No When YES client is asked to create a password and verify the password *OR* Client clicks yes Email is sent to client with a link to reactivate their account Client clicks on link and is directed to add a new password and verify new password {color:#de350b}KJA - There needs to be some type of authentication process .
ISERVE-179 | Story | ISERVE-11 | Login: 2. User Account Login | As an iServe Nebraska Portal account holder, I want to be able to login to the iServe Nebraska Portal with my username and password so I can quickly navigate to other functionality. * {color:#de350b}User should be taken to the main screen upon successful login unless logging in during application process. * {color:#de350b}User can login from the iServe portal or at the start of completing the multi-benefit application. * {color:#de350b}User should have the ability to toggle between showing and hiding password while entering on login screen. * {color:#de350b}User should have ability to store password locally on the device they are using to access the site. Workflow: * User enters username / password successfully * User views iServe Nebraska dashboard +Questions:+ * Can username/password be saved on device so it does not need to be entered again?
ISERVE-177 | Story | ISERVE-11 | IAM: 12. New User: Set Up User Password Recovery | As a new iServe Nebraska Portal user, I want to specify password recovery options for my iServe Nebraska account so I can reset my password. {color:#4c9aff}*Recommendations* * {color:#4c9aff}Security questions should be completed at time of account creation ** {color:#de350b}Available questions for authentication will be determined by B2C/G2C vendor implementation. ** {color:#4c9aff}Require a minimum of 3 security questions for users to provide ** {color:#4c9aff}Users are not allowed to select the same question multiple times * {color:#4c9aff}Account recovery can be setup for any account on the iServe Nebraska Portal * {color:#4c9aff}User will be prompted at account creation to provide a email address and mobile phone number ** {color:#4c9aff}These could then be utilized for password recovery {color:#4c9aff} *Messaging* * {color:#4c9aff}Duplicate question ** {color:#4c9aff}+Trigger+: The same question is selected multiple times for security questions. ** {color:#4c9aff}+Message+: You must select three different security questions to answer. * {color:#4c9aff}Security Answer is left blank ** {color:#4c9aff}+Trigger+: One or more of the answer fields is left blank ** {color:#4c9aff}+Message+: You must answer all security questions.
ISERVE-174 | Story | ISERVE-11 | Maintain Account: Enter Profile Information | As a new iServe Nebraska Portal user, I want to provide basic demographic information for my iServe Nebraska profile so that my contact information and communications preferences are recognized and utilized by the iServe system. As an existing iServe Nebraska Portal user, I want to be able to update my demographic information for my iServe Nebraska profile so my contact information is up-to-date. * Available fields to populate: ** First Name (Required) ** Last Name (Required) ** Physical Address (Required) *** Address line 1 (Required) *** Address line 2 *** Address line 3 *** Zip Code (Required) *** City (should auto-populate from zip code) *** State (should auto-populate from zip code) (abbreviation) ** Mailing Address (Optional) *** Address line 1 (Conditionally Required) *** Address line 2 *** Address line 3 *** Zip Code (Conditionally Required) *** City (should auto-populate from zip code) *** State (should auto-populate from zip code) (abbreviation) ** Telephone Number (Optional) *** Select a type: **** Mobile **** Home (default) **** Work **** TDD (hearing impaired) *** Enter a number (formatted in 10-digits) *** Allow user to enter multiple numbers ** Email Address (Optional) ** Preferred Method of Communication (Required) *** Options: email, text, phone, or mail ** SSN (Optional) ** Language Preference (Required) *** Available options: TBD *** [^CID 535010 State of Nebraska-Language Usage report 2019.RTF] *** [^CID 535010 State of Nebraska-Language Usage report 2020.RTF] ** Alien Number (Optional) ** DOB (Optional) ** Document/Card Number (Optional) ** Passport/country of Origin (Optional) ** Naturalization Number (Optional) ** Citizen Certification Number (Optional) *Messaging* * Zip code not matching ** +Trigger+: Prompts when zip code and city/state combination are not correct ** +Message+: City, State, and Zip Code combination are not correct, please review. ** {color:#de350b}+Question+: What happens when zip code occurs in multiples states or cities? ** {color:#de350b}+Question+: Do we have the list of validate zip, city, state combinations? * Phone number format ** +Trigger+: Prompts when phone number entered is NOT 10 digits. ** +Message+: Phone number does not meet criteria please enter a valid 10-digit phone number. ** +Note+: The UI will take the entered digits and format it into the (XXX) XXX-XXXX format. ** +Note+: System should accept entry of just 10 digits OR standard phone format * Email format ** +Trigger+: Prompts when email address does not conform to expected standards. *** Require an "@" and a "." to be valid ** +Message+: Please enter a valid email address. ** +Note+: We are not verifying the email at this stage, just validating it conforms to standard email address syntax. * Required field left blank ** +Trigger+: Prompts when any fields that is denoted as required is not provided. ** +Message+: Please enter _XXX_ field. ** +Note+: Display as text above the field.
ISERVE-173 | Story | ISERVE-11 | New User: Create iServe Account | As a new iServe Nebraska Portal user, I want to create an iServe Nebraska account with a username and password so that I can be sure my account is secure. * Username must be unique across all accounts, regardless of status, within the iServe authentication system * Username must be numbers or letters and cannot contain special characters or symbols * If username is already in use, system should provide examples of other options based on provided username value. * Password must be entered twice for user input validation * Password must meet criteria: ** Case sensitive ** Must be 8-10 characters in length ** Include at least 1 number ** First character cannot be numeric ** No symbols allowed ** Characters cannot be sequentially repeated more than twice ** Passwords must be different than previous password ** One lower case letter ** One upper case letter ** Cannot include the following phrases: Password, Huskers, Admin * Password criteria should be displayed/available to user when entering password details. * User should be prompted to verify they are not a robot ** Specific method up for later design discussion with vendor and architect team *Messaging* * If username is a duplicate/unavailable ** +Message+: Username is not available. * If password does not conform to criteria ** +Message+: Password does not meet password criteria. Please review criteria and reenter password.
ISERVE-151 | Story | ISERVE-11 | IAM: 13. New User: User Verification of New Account Setup | As a new iServe Nebraska Portal user, I want to be notified when my new account is established so that I can verify that I did set up the account +Overall Workflow+ * At time of account creation new user is prompted to specify a verification method for the new account (ISERVE-532). * Account verification is triggered. * User has specified time period for verification to be valid (ISERVE-533) * If User exceeds the verification period (ISERVE-533) then the user can retrigger a verification process (ISERVE-334) +*Feature*+++: Account Verification Process +Scenario+: Verification via Phone *Given* a new user choses to verify account setup via phone *When* the account request is submitted *Then* the new user receives a phone verification +Scenario+: Verification via Text *Given* a new user choses to verify account setup via text *When* the account request is submitted *Then* the new user receives a text verification +Scenario+: Verification via Email *Given* a new user choses to verify account setup via email *When* the account request is submitted *Then* the new user receives an email verification +Scenario+: Verification via PIN *Given* a new user does not have an email or phone *And* the user still wants to verify their account *When* the account request is submitted {color:#ffab00}*Then* {color:#ffab00}the new user will be {color:#ffab00}+_mailed_+ {color:#ffab00} a PIN to verify the new account. +Workflow+: * System prompts user with several options for user to verify account creation * User selects (phone, email, or text) * If user does not have access to a phone or email for verification purposes, the system will provide a temporary PIN * If user verifies account creation within pre-defined time period then user will continue to password creation (US #....) * If user does not verify account creation within pre-defined time period then system saves username ** username is deleted after a _*configurable*_ period of time +To Do+: * Screen Mockup ** how does user interact with homepage UI to verify a username? Display of options for verification. ** Help content for verify username options ** Determine what user messages we need for this verification step * Determine/Finalize verification methods: Phone, Email, text * {color:#de350b}Do we to still offer PIN? * Determine predefined time period for verification [Per procurement flow: Time period will be predefined based on DHHS business rules] ** {color:#ff0000}Nicole - A good timeframe for the verification would be around 10 minutes from the time the PIN was sent, after that a new PIN should be requested. * Define time period for system to hold username before deleting if never activated ** {color:#ff0000}Nicole - I think somewhere between 6-12 months the system should hold the username before deleting. If an account has not been accessed in that timeframe, a new account would need to be created. If they check their account at least once during the timeframe, the system should keep that as a valid username. For EA, depending on the recertification period, apps are only needed once every six months or 12 months if they are elderly/disabled waived or completed a timely recertification with interview held in the past 12 months. If there are no changes in the middle of recert, the clients typically will not contact the agency until the next recert is needed. * Ability for a user to request activitation after no responding to notification in a timely manner... ** {color:#ff0000}Could we have it set that a client is sent the link or the pin and have it be active for 24 hours, and within that message, allow for the client to resend that link or pin if needed? I almost feel after the initial timed period, the process should just start anew. ** {color:#ff0000}Nicole - I would say 10 minutes would be sufficient time for a client to retry verification. If they fail to submit verification, a new code/PIN would need to be requested.
ISERVE-47 | Story | ISERVE-11 | IAM: Account Deactivation: By User | As an iServe Nebraska Portal user, I need to be able to deactivate my Portal Account when my account is no longer needed. Scenarios: 1. User deactivates their active account * {color:#de350b}User must verify identity (example: series of security questions) * {color:#de350b}Pop up appears for user to confirm they wish to deactivate account * {color:#de350b}Email is sent to user to verify account has been deactivate with brief instructions on how to reactivate account in the future 2. User attempts to deactivate an account that is not theirs * {color:#de350b}User must verify identity (example: series of security questions) * {color:#de350b}Email is sent to user that attempt on their account for deactivation * {color:#de350b}Email has link for user to reset password * {color:#de350b}Verification email sent out to user when password has been reset successfully and user is automatically redirect to portal 3. User attempts to access an inactive account - {color:#de350b}Reference ISERVE-186 * Message pops up account is currently inactive - do you wish to reactive account? ** {color:#de350b}User says yes - email is sent to last known email address ** {color:#de350b}User says no - no further action needed 4. User deactivates account by mistake - {color:#de350b}Reference ISERVE-186
ISERVE-36 | Story | ISERVE-11 | Client Language Preference on Account Details | As an iServe Nebraska Portal user, I would like to log into the iServe Nebraska Portal using my preferred language so that I may best understand the information being asked/presented to me. * User should have option to specify a preferred language for communication * Value should be available to populate at account creation or on the edit account screen * Value is required but should have a default value of 'English' for both field. * If Written communication is updated and saved with a value, the system should immediately refresh into the specified language for the user. * List of available languages to be determined in future refinement effort.
ISERVE-24 | Story | ISERVE-11 | IAM: Role Base Access | As an iServe Nebraska Portal user, upon logging in to iServe Nebraska Portal, I want to be able to choose from all functionality that is applicable to me. {color:#de350b}(By allowing stake holders to choose their functionality would also add the roles to that functionality, do we want to allow that much control in the hands of the stake holders, or will the stakeholders be provided with initial username so that the roles are assigned to them before they start? How would this affect their access levels?) Stakeholder Types: * Applicant * Client * Parent or Legal Guardian of Client * Authorized Representative of Client * NE DHHS staff ** {color:#de350b}Workers ** {color:#de350b}Lead Worker ** {color:#de350b}Supervisor ** {color:#de350b}Administrator ** {color:#de350b}Help Desk ** {color:#de350b}Production Support ** {color:#de350b}IT Department * Healthcare Providers * NE DHHS Health Navigator / Community Health Worker * Community Partner Staff * Social Services Agency Staff * Employment Entity Staff * {color:#de350b}Nursing Home staff
ISERVE-12 | Story | ISERVE-11 | IAM: User Preferred Identity | As an iServe Nebraska Portal user, I want to use my preferred identity provider (Social IDs, email, local accounts, business & government ids) to gain access to iServe Nebraska so I don't need to remember another username/password. +Stakeholder List+: * Applicant * Client * Parent or Legal Guardian of Client * Authorized Representative of Client * NE DHHS staff * Healthcare Providers * NE DHHS Health Navigator / Community Health Worker * Community Partner Staff * Social Services Agency Staff * Employment Entity Staff If user runs into issues, user is prompted with message to contact DHHS {color:#ff0000}GK - I would like to add a security question as well to provide an added layer of security. {color:#0747a6}{color:#ff0000}{color:#0747a6}KJA - I agree {color:#0747a6}that the log in process needs to be as secure as possible. I think there should at least be an option to turn on multi-factor authentication. If I was a customer, I would want this. I do not think using Social IDs is a good idea for this situation.
ISERVE-13 | Story | ISERVE-11 | IAM: Create Account - Using NE DHHS Account | As an existing AccessNebraska user with a NE DHHS account, I want to use my AccessNebraska information to enter iServe Nebraska Portal so I don't need to sign on with a username/password to the application. * {color:#4c9aff}What happens when the username/password constraints are not the same? * {color:#4c9aff}What happens when the username is already taken? * {color:#4c9aff}What happens when the account does not have an active master/program case? * {color:#4c9aff}What happens if the account has not been used for 90 days? 6 years? * {color:#4c9aff}How do we ensure we are not carrying over duplicates? * {color:#4c9aff}What if we do not have all the required fields for the new iServe accounts? * {color:#4c9aff}Password syncing will not be done between the systems so once you update iServe then the accounts no longer match. {color:#de350b}Mickey - Existing AccessNebraska Account Users should be able to use same log on credentials in IServe Portal. User may have the option to change password once logged in if they wish. {color:#de350b}Existing AccessNebraska Account information should transfer automatically to IServe Portal. User will be able to update information without resistance {color:#de350b}If user has issues using current AccessNebraska credentials to log on to IServe Portal, pop up will appear to contact DHHS with contact information for assistance {color:#de350b}Nicole - Login information from the current Access Nebraska site should be transferable to the iServe Nebraska Portal. For first time login, the system should require a password update. If the client is not sure of their current username there should be an option for them to use identifying information to have an email sent with their username provided. Once signed in with the username, as stated above, a password update should be required to make sure the account is secure. {color:#de350b}Given that they have any other issues or questions, they should contact Access Nebraska for help. {color:#de350b}I think it is necessary for workers processing benefits or working with clients to have access to the iServe Portal. It would also be a good idea to have Help Desk and P&S to have access to the portal. {color:#4c9aff} What is P&S? If user runs into issues, user is prompted with message to contact DHHS
ISERVE-584 | Story | ISERVE-54 | iServe Content: Benefit Discovery | As an iServe visitor, I want to clearly find the Benefits Discovery tool so that I can use this resource to determine potential benefits. This section/link must meet iServe design criteria. *Scenarios:* 1. Site visitor is not logged into an iServe account and navigates to benefit discovery 2. Site visitor is logged into an iServe account and navigates to benefit discovery
ISERVE-527 | Story | ISERVE-54 | iServe Content: Account Creation & Login | As an iServe visitor, I want to clearly find the way to create and/or login to an iServe Nebraska account so that I can fully access the iServe resources. This section/link must meet iServe design criteria.
ISERVE-59 | Story | ISERVE-54 | iServe Content: File Upload | As an iServe site visitor, I need to be able to easily find where I can upload supporting/updated documentation so that I don't have to send in a hard copies for DHHS. This section/link must meet iServe design criteria. *This story addresses where is can be found and how it is displayed (UX/UI) not the functionality of file upload *Scenario* 1. Site visitor is not logged into an iServe account and navigates to file upload 2. Site visitor is logged into an iServe account and navigates to file upload *Comments to be reviewed later* - ?'s - do all site user "roles'/persona need the same capabilities? Any additional requirements/other behaviors that differ by role? {color:#de350b}There should be different Roles for file uploads per user account (POA, Guardians, Clients, Business Clients \{Nursing Homes etc}) Do we need to have a separate story for renewals vs new app? or, will both go through same "path"? {color:#de350b}Initial and Renewals should be two different stories for upload. Example: I am applying for the first time, I should be able to attach files that are needed for verification of the different sections of the application, such as bank statements, life insurance policies, utility bills, rental agreements just to name a few. {color:#de350b}Renewal should be viewed as information that we already have on file, that the client can update and submit any changes such as employment, address, contact preference, phone number and additional household members or members that are no longer in the household and have the option to upload verification of paystubs, utility bills etc. - list out all "formats" of uploads: pdf, image/photo, €¦ €¦ €¦. OR, do we put this in the actual file upload story? this story is just about finding where to do it... {color:#de350b}Mickey - This is very similar to ISERVE-78 my comments from ISERVE 78 was as follows: {color:#de350b}Common file extensions: * {color:#de350b}Doc/Docx * {color:#de350b} Txt * {color:#de350b} xlxs * {color:#de350b} PDF * {color:#de350b} HTM/HTML * {color:#de350b} Tif/Tiff * {color:#de350b} Gif * {color:#de350b} Png * {color:#de350b} Raw €“ not used much with common users {color:#de350b} {color:#de350b}File upload capability should be only accessed if the individual has an active account (example: client, shareholders, and workers) {color:#de350b} {color:#de350b}If an individual is able to maneuver a website then they should be able to sign in to an account. {color:#de350b} {color:#de350b}If a File Upload link is on the home page when clicked should take the user to the log in page. (restrictions for who can upload files, otherwise anybody could just upload random files at will) Or a pop up message saying you are being redirected to the log on page once logged on the client will be connected to the upload page {color:#de350b} {color:#de350b}I don €™t feel we need an actual file upload story, all the information can fall under file upload.
ISERVE-60 | Story | ISERVE-54 | iServe Content: Email Messages | As an iServe site visitor, I need to quickly find where to +send / receive secure messages+ so I don't immediately call DHHS for assistance. This section/link must meet iServe design criteria.
ISERVE-53 | Story | ISERVE-54 | UX/UI: Navigation & Layout | As a site visitor, I want intuitive navigation and site usage so that I can find the resource I need and complete any of the available activities. This includes: * Placement and layout of menus, navigation bars, widgets/tiles/content, links, and other site resources. * Use of navigation tools such as keyboard, mouse, and touchscreen ** Including Talk to touch ability when mobile screen can't be used and selection is needed ** Cancelled some stories and added them as ACs to this story *** ISERVE-541 *** ISERVE-540 *** ISERVE-550 *** ISERVE-551 *** ISERVE-549 * Ability to move between activities, screens, as well as get back to home or other recognizable site locations. * Large tap targets, wide buttons, and chunky dropdown inputs
ISERVE-52 | Story | ISERVE-54 | iServe Content: Online application "Apply for Benefits" | As an iServe visitor, I want to clearly find the online application so that I can start/continue the online application without calling DHHS or applying via paper. This section/link must meet iServe design criteria. Scenarios: 1. Site visitor is not logged into an iServe account and navigates to the online application 2. Site visitor is logged into an iServe account and navigates to the online application
ISERVE-39 | Story | ISERVE-54 | Homepage - Login - Legal Disclaimers | As an iServe Nebraska Portal user, I would like to be notified that I am on a government site and its proper uses so that I am protected for legal liability issues while using the Portal. Current disclaimer on AccessNebraska on Login: THIS IS A GOVERNMENT COMPUTER SYSTEM. UNAUTHORIZED ACCESS IS PROHIBITED. ANYONE USING THIS SYSTEM IS SUBJECT TO MONITORING. UNAUTHORIZED ACCESS OR ATTEMPTS TO USE, ALTER, DESTROY OR DAMAGE DATA, PROGRAMS OR EQUIPMENT COULD RESULT IN CRIMINAL PROSECUTION.... Current disclaimer on AN when creating an account: THIS IS A GOVERNMENT COMPUTER SYSTEM. Unauthorized access, use, misuse, or modification of this computer system or of the data contained herein or in transit to/from this system constitutes a violation of Title 18, United States Code, Section 1030, and may subject the individual to Criminal and Civil penalties pursuant to Title 26, United States Code, Sections 7213(A), 7213A (the Taxpayer Browsing Protection Act), 7431 and Health Insurance Portability and Accountability Act of 1996. If monitoring reveals possible evidence of criminal activity, such evidence may be provided to Law Enforcement Personnel. Additional information may be found at the Nebraska DHHS System Website Disclaimer under 'Disclaimer'. The Home Page of AccessNebraska also contains a link to a €˜General Disclaimer €™. [http://dhhs.ne.gov/Pages/disclaim.aspx]
ISERVE-18 | Story | ISERVE-54 | UX/UI: Access iSERVE from various Web Browser | As an applicant, I want to access the iServe Nebraska Portal using an internet browser of my choice so that I can get to benefit resources from my device. ACCESSNebraska is available on 3 web browsers; Firefox, Internet Explorer and Google Chrome.
ISERVE-572 | Story | ISERVE-44 | Gauge User Experience | As an Organization Change Manager I need the ability to add a survey to the Portal to gage the user's experience on usability.
ISERVE-496 | Story | ISERVE-44 | Redirect USDA SNAP from AccessNebraska to iServeNebraska Portal | Redirect USDA SNAP State Directory of Resources from AccessNebraska to iServeNebraska [https://www.fns.usda.gov/snap/state-directory]
ISERVE-195 | Story | ISERVE-44 | UX/UI: Fonts, Colors, Imagery, Icons, Logo | As a site visitor, I want a visually appealing iServe experience and to be able to recognize that I am on an official state site so that I am comfortable using the online resources for state benefit programs. Considerations: Fonts, Colors Imagery Icons Logo Acronyms (identify and define here. Note as AC on content stories) {color:#00875a}Need to attach marketing standards
ISERVE-46 | Story | ISERVE-44 | AccessNebraska - Redirect New Accounts | As a new iServe Nebraska Portal user, I want to be redirected from AccessNebraska to the iServe Nebraska Portal when trying to create a brand new account so I am not confused where or what to do to begin my journey with DHHS Benefits and Services. {color:#de350b}Mickey - We currently have another story related to this one ISERVE-63 where comments have been added {color:#de350b}Referring to Rebecca's comment below - when we are ready to utilize Iserve solely, programmers can redirect the accessnebraska.gov site automatically to the Iserve site. Example: I have accessnebraska saved as a favorite i open the site and it automatically takes me to a page that states that I am being redirected to the new site Iserve Nebraska. This works alot like call forwarding.
ISERVE-28 | Story | ISERVE-44 | UX/UI: Access iServe from various devices & different size screens | As an iServe visitor, I want to access the iServe site from various devices with different size monitor screens so that I can manage my benefit needs on my preferred device. This includes: Large/XL monitors for a PC or MAC Laptops Tablets/iPADs Mobile phones {color:#00875a}Need to add resolution/pixel details for each size device
ISERVE-643 | Story | ISERVE-350 | iServe Nebraska - What's New | As an external DHHS customer, I want to be informed on changes to iServe Nebraska so that I can use new features or understand changes to existing features. Include: * Announcements * Coming Soon _We're sharing details about our planned releases, but keep in mind that we might need to make changes to release dates and the features themselves. You can subscribe to this article to get updated about any changes._ {color:#FF0000}_MS - Having a banner on the access nebraska home page would be an ideal location to make announcements, they could then click on the banner that will redirect them to the upcoming changes. It would also be nice if when it redirects them, it shows a history of change announcements for the users. This way if they missed anything they could catch up on the information that was released_
ISERVE-640 | Story | ISERVE-350 | AccessNebraska User Tips | As a system admin, I want the user tips pdf on AccessNebraska to reflect accurate details when iServe Nebraska Portal is in Production. !image-2021-04-29-14-34-28-890.png¦width=101,height=128!
ISERVE-539 | Story | ISERVE-350 | Help Content Knowledge Search | External: As a client, I can use free-text search so that I can find the help I am looking for. * Need to use boolean operators AND and OR * fuzzy search * search by single words and phrase
ISERVE-352 | Story | ISERVE-350 | Online Help - Integrated Eligibility Application | Knowledge Base 2: Completing the Application External - As a visitor to iServe Nebraska, I want information about how to use the single application "IE Application", what it means, how to do it, so I can understand how to apply for benefits. {color:#57d9a3}Nicole & Kristi - A help button that pops up can state "Chose the programs you wish to apply for and fill out the application by following the prompts for each section" This would be good placed next to the Save/Next Page button at the bottom of the screen. {color:#4c9aff}MR - Will this be in a FAQ section or a section on the page itself?
ISERVE-351 | Story | ISERVE-350 | Online Help - Benefit Discovery | Knowledge Base 1: Do I Qualify External - As a visitor to iServe Nebraska, I want information about Benefit Discovery, what it means, how to do it, can I do it without sharing personal information so I can understand how to use the Benefit Discovery Tool. {color:#4c9aff}MR - Where will this information be located? Will it link to a separate page with this information or in a FAQ page? {color:#4c9aff}MD - * {color:#4c9aff}Benefit Discovery help will be located in the FAQ page * {color:#4c9aff}Accessible to all individuals for viewing * {color:#4c9aff}No username or password needed to view the FAQ * {color:#4c9aff}Search option needs to be available to search the FAQ ** {color:#4c9aff}Question - How do I apply for benefits *** {color:#4c9aff}Answer - " " ** {color:#4c9aff}Question - How do I decide which benefit I would like to apply for? *** {color:#4c9aff}Answer - " " {color:#de350b}KJA - The programs that are included in benefit discovery should be listed with links to further information about each program. "Learn More About This" link which will take them to the benefit discovery section of Help where it should explain what this process is and tell them what information is needed to complete, that this is not an application and that they will have the option to complete an application after completing the benefit discovery questionnaire. Screenshots should be included. Possibly a short tutorial video could be available.
ISERVE-355 | Story | ISERVE-350 | Online Help - Messaging | Knowledge Base 5: Sending and Receiving Messages External: As a visitor to iServe Nebraska, I want information about sending and receiving messages in iServe Nebraska including but not limited to: * How to set up my inbox * How to access my inbox * How to see sent messages * How to delete a message * How to create a message to DHHS * How to upload an attachment to message * How to respond to messages * How to view history *
ISERVE-354 | Story | ISERVE-350 | Online Help - File Uploads | Knowledge Base 4: Uploading Documents External - As a visitor to iServe Nebraska, I want information about file uploads including but not limited to: * What can I upload{color:#ff0000} (input type and size) ZC * How can I upload * Is my information secure * How long are my uploads available * How to see my previously uploaded files * Who to contact if I have problems * FAQ * {color:#ff0000}can i edit or delete my files ZC * {color:#ff0000}If i fail to upload, i'd like an error message and a reminder prompt of limitations
ISERVE-353 | Story | ISERVE-350 | Online Help - Portal Account and LogIn / LogOut | Knowledge Base 3: Creating an Account External - As a visitor to iServe Nebraska, I want information about what is an iServe Nebraska Portal Account, how to get one, who needs one, what can I do once I have an account so that I understand my abilities in iServe Nebraska. {color:#4c9aff}MR - Will this be its own section, or in an FAQ or a link at the bottom?
ISERVE-231 | Story | ISERVE-350 | Training and Help - Admin | Internal: As a Training Lead/Coordinator, I want the ability to integrate a Learning Management system with the Portal MVP to provide training to DHHS Staff on functionality relevant to their roles and their ability to assist Nebraskans using the Portal.
ISERVE-35 | Story | ISERVE-350 | Training and Help - System Help | External: As a DHHS Client, I want help guides and documentation so I can solve my own issues with using the system. Wish List: FAQ User Guides Tool Tips (Clarification on field entry like a ? icon) Help icon €“ upper right with keyword/phase capability Job aids €“ within the system (in addition to dynamic help)
ISERVE-626 | Story | ISERVE-547 | Key Performance Measures - Public Monthly Report | As a Nebraskan, I want to know that DHHS is continuously making improvements to serve us better. {color:#de350b}GK - As a Nebraskan, I want to have easily accessed reports that demonstrate DHHS is continuously making improvements in it's programs and systems to serve us better. Note: Monthly reports are available via AccessNebraska and will need to include data from Portal MVP applications and possibly need to be available on Portal at Go-Live. [https://dhhs.ne.gov/Pages/ACCESSNebraska-Performance-Measures.aspx]
ISERVE-196 | Story | ISERVE-547 | Audit and Reporting: Audit Trails | As a system (iServe), I need to be able to track activities within the system so that I can produce audit trails as required for controls, investigation, research, etc.
ISERVE-197 | Story | ISERVE-547 | Regulatory Reporting | As regulatory reporting liaison, I need to be able to receive, generate or requests reports in order to effectively report application data to CM/FNS.
ISERVE-327 | Story | ISERVE-545 | iServe Content: Register to Vote | As an applicant, I would like to be informed about voter registration so I can chose to register if I want. This section/link must meet iServe design criteria. *Consideration* Current state is that we must allow clients to register to vote when they are in contact with DHHS. ATM we comply with this by having this in renewals and applications. This to be discussed in next policy call to understand the minimum requirements [~rebecca.peplinski] *Design* Screen Mockup: * Should there be a form to access - ** {color:#0747a6}KJA - The link to a printable PDF should be available - ([https://sos.nebraska.gov/elec/pdf/vrfillable.pdf]) * Should the client be redirected to a site ** {color:#0747a6}KJA - The link to the online voter registration should be available - ([https://www.nebraska.gov/apps-sos-voter-registration/]) * Should DHHS continue to send the form to client, upon request ** {color:#0747a6}KJA - Yes, the option to request a paper form be mailed should be available * {color:#ff0000}GK-The question "If you are not registered to vote where you live now, would you like to apply to register to vote today?" should continue to appear on the IE application both on the portal and on the paper form before the signature. A link to the Secretary of State website to fill out the form online should also be included on the portal website.
ISERVE-542 | Story | ISERVE-625 | Role Based Access Control | As a system administrator, I want to be able to create a new user role to manage system access.
ISERVE-340 | Story | ISERVE-43 | Upload Files: 2. User Selects ability to upload files | As an iServe Nebraska Portal user, I want to access the file upload functionality from the Portal mainpage (ie. Homepage / Dashboard) so that I can upload files to my Portal Account. {color:#ff0000}Nicole - As a Portal user, I would like to have a section on the mainpage with links to important locations on the website. File Upload would be one of those to include so the user can easily access the needed page to submit documents for the application. {color:#ff0000}MD - As a Portal user, I would like to have a section on my portal page with links to most used features such as File Upload To Do: UI/UX
ISERVE-341 | Story | ISERVE-43 | Upload Files: 3. Applicant/Client Chooses Files for Upload | As an iServe Nebraska Portal account holder, I want to select one or more files from my personal/local computing device (e.g. laptop/desktop or mobile device) to upload so that I can use these files within iServe Nebraska Portal. To Do: * UI/UX {color:#ff0000}GK-As a portal user, I want easy step by step instructions on what to do. * List of file types allowed {color:#ff0000}GK-Currently through ACCESS Nebraska, tiff, jpeg and pdf with 1mb maximum size are accepted. As a user of the portal, I want to be able to select Word or Excel documents to upload as well as photos I take directly from my phone. I want an increase of a size limit on my files if possible as sizing is not easy for clients with limited knowledge of how to do so. * Where can this come from local drive, drop box etc? {color:#ff0000}GK-Currently this can only be uploaded from a local drive. Clients can only send secure files from another source through ANDI. As a user, I would like to be able to use Drop Box or Google Cloud if possible. ** {color:#0747a6}KJA - Mobile and desktop support. Multiple file upload. Drag & drop. Progress indicator. Preview of documents. Notification message that (#) documents have been successfully uploaded. Able to cancel/ resume. Able to rename / label. Able to choose which household member(s) to attach documents to. Alert is generated for worker.
ISERVE-342 | Story | ISERVE-43 | Upload Files: 8. User Notification Successful File Upload | As an iServe Nebraska Portal Account holder, I want to be notified that my file(s) were sucessfully uploaded to my Portal account. Questions: What is the wording of this message? MD * "Your documents have successfully uploaded to your account"
ISERVE-339 | Story | ISERVE-43 | Upload Files: 6. Rename Files | As an applicant. upon file upload I want to be able to label or rename my uploaded files so I can customized those file at my preference. Questions: What are the limitations? MR - Are we going to have certain names or labels only available, like Expenses or Resources? Or can they name them or label them whatever they want? GK - A drag down menu should be available with set labels to choose from. The ability to type a limited description should additionally be available. Example: Label - "Income" Description - "I don't have paystubs but here is my bank statement showing deposits." The alert should go out based on the label provided. MS - A list of labels was added to attachments the spreadsheet is a close representation of items that we receive - I dont feel we need to allow the clients to "rename their files" we need to give them an option of what category the upload falls under" not only will this assist the client but it will also assist the workers since it will automatically then populate in the correct area in DI. "As an applicant, upon file upload I want to be able to add a label to the upload file so I can customize what is being submitted" Instead of Renaming Files "Adding labels to Files"
ISERVE-338 | Story | ISERVE-43 | File Uploads 5a - User Notification File Compliance Check | As an applicant. upon selecting file(s) for upload I want to be notified if my files were not acceptable so that I can address the issue. Questions: What is the wording of this message? What are the technical constraints? What DHHS security and/or program policy requirements are forces on this functionality?
ISERVE-223 | Story | ISERVE-43 | Upload Files: 5a. Document Resolution Validation | As a Portal Account holder attempting to upload file(s), I want information on how to make my file resolution compliant so I can successfully load my file(s)
ISERVE-191 | Story | ISERVE-43 | Upload Files: 9. Applicant file upload within IE Application Submission | As an applicant, I want to upload documentation during IE Application submission to support my application for faster eligibility determination. Scope: This story is specific for uploading attachments to an IE application during the IE Application Process. Process Flow: * User selects ability to upload files (including but not limited to: Drivers License, Birth Certificate, Tax Returns, Pay Stubs, Verification of Expenses(Student Loan Interest), Utility Bills, Guardianship paper work, auth rep forms). * System provides ability to select one or more files on their local computing device * User selects files on local device * System checks files for file size/type compliance * If files are not compliant - user receives system message * System allows user to label (rename) uploaded files * System saves uploaded files to user Portal account * System displays message confirming that the files have been successfully saved * User associates uploaded files with IE Application * System displays message confirming the files have been associated to the IE Application * System provides notification to DHHS staff that uploaded files have been associated with IE application ToDo: * Process Flow above needs reviewed/confirmed - this is from procurement process flow 6 * Screen Mockup - how does user interact with UI to upload files * Identify technical constraints size/number/type of files eligible for upload TYPE: File formats include, but is not limited to: jpg, pdf, doc, docx, xls, xlsx, csv, tiff SIZE: 1MB is the current constraint prefer more if possible NUMBER/QUANTITY: Current state no limit on number of attachments until size limit is reached. * Identify where files can be uploaded from: local computing device/cloud/dropbox/camera roll * Identify wording of notifications/messages in above Process Flow
ISERVE-189 | Story | ISERVE-43 | Upload Files: 1. Help (Instructions) | As an applicant/client, I want to view instructions(aka. help) on how to upload files so I can properly load a file to my account or application for benefits. Questions: * Will users upload documents to account or application or both? Procurement leads to both ways. Is this true? * If file is uploaded to application is it then "saved" to the user account [document repository] for future use/reference? ToDo: * Create Mockup of instructions on page * Create detailed instructions ** _"You may upload up to XX documents that will be attached to this application. EACH document/item must be less than XXMB in size."_ * Determine technical constraints...NOTE: there are pain points here from AccessNebraska. We have identified a few pain points with this process: * At times, users cannot be verified as unique, so properly indexing can be difficult * ** If clients have similar DOB, last 4 of SSN, or First and Last names * There are currently not proper instructions on what type of files may be uploaded or what the maximum size allotment for these files * {color:#FF0000}GK-There are instructions found in the help section for types of files and sizes, as well as instructions to mail us if they are unable to upload themselves. * ** When files are not ready to be submitted due to size or type constraints, the "submit" or "upload" is greyed and unable to be used * There is currently not a process to delete a document that has been uploaded without writing a formal request to do so * If an uploaded document pertains to more than one HH member, the document would either be assigned to 1 HH member or need to be uploaded concurrently to allow for it to be assigned to multiple members ** This is important so as clients migrate to other MC and Programs, that this information follows as well I will continue to update this if come across other Pain Points
ISERVE-27 | Story | ISERVE-43 | Upload Files: 7. Applicant/Client Upload Saved to Account | As an iServe Nebraska Account Holder, I want the file(s) I selected to upload saved to my iServe Nebraska Portal account so I can use these in my application and communication regarding benefits and services. Scope: This story is specific for uploading to a user document repository outside of application process. For example: application was already submitted and DHHS requested additional documentation. To Do: * UI/UX
ISERVE-686 | Story | ISERVE-687 | Government Cloud Development | Implement Government Cloud
ISERVE-611 | Story | ISERVE-687 | Commercial Cloud Development | Implement Commercial Cloud
ISERVE-606 | Story | ISERVE-687 | Create CICD Pipeline
ISERVE-582 | Story | ISERVE-546 | UX/UI: Accessibility for multiple languages | As a site visitor, I need the content to be accessible to me in a language I know so that I can understand the information and instructions provided.
ISERVE-581 | Story | ISERVE-546 | UX/UI: Accessibility for reading | As a site visitor, I need the content to be accessible to me and read at a 4th grade level so that I can understand the information and instructions provided.
ISERVE-583 | Story | ISERVE-546 | UX/UI: Accessibility for text to speech | As a site visitor, I need the content to be accessible to me when using a text to speech tool so that I can hear and clearly understand the information and instructions provided. This includes making sure the layout is such that a reader can logically move through text. *Consideration:* Too much "stuff" in a site may delay visitor from quickly getting to necessary information as they cannot quickly scan and skip over text.